## Project Information
-In an operations case competition, our team has to invent a project, design a model, and present it to the board.
-Table 1 shows the steps necessary for the project to be completed. The durations represent the ideal time needed to spend on each step in order to ensure a project of the highest quality.
-Network representation is shown in the powerpoint file
-In sheet "Finding Critical Path", solver finds the critical path and minimum time needed to complete the project. (see figure 1)
-This shows that the critical path is A => C => D => E => G => H, and the minimum time required is 28 hours. This can also be seen in sheet "Answer Report 1" |  |  |  |  | Figure 1
-However, for the competition, we are limited to 24 hours to complete all of these activities.
-Table 2 outlines which activities can be reduced, and how much that will affect the quality of the presentation.
-Some activities can be reduced more than others. Reduction of different activities holds varying penalties to the quality of the presentation.
-Solver is run to minimize the penalty to the quality of our presentation (see figure 2)
-Additional crashing information is found in sheet "Answer Report 2" and sheet "Sensitivity Report 2"
-We also wanted to know how our optimal quality would decrease with less and less time, so we ran solver table on sheet "Solver Table" (see figure 3)
-Finally we graphed the how the decline in quality diminishes as the time limit increases (see sheet "Quality decrease chart")
Table 1
|  | Required activities | Preds. | Duration (hours)
| A | Planning Meeting |  | 3
| B | Defining objective function and decision variables | A | 2
| C | Research | A | 7 | Figure 2
| D | Defining constraints | C | 3
| E | designing model | B,D | 7
| F | Meeting with Juran | E | 2
| G | Design Presentation | E | 6
| H | Practice | F,G | 2
Table 2
| Cost of reducing | Maximum reduction
| 3.5 | 2
| 4 | 0.5
| 1.5 | 2.5
| 2.5 | 1.5
| 2.75 | 3
| 4 | 0.5
| 2.5 | 3
| 3 | 1 |  |  | Figure 3

## Finding Critical Path
[6 empty] | Minimum time required | 28
[12 empty] | Required activities | Preds. | Duration
| t0 | t1 | t2 | t3 | t4 | t5 | t6 |  |  |  | A | Planning Meeting |  | 3
| 0 | 3 | 10 | 13 | 20 | 26 | 28 |  |  |  | B | Defining objective function and decision variables | A | 2
[11 empty] | F | Meeting with Juran | E | 2
| t0 | t1 | t2 | t3 | t4 | t5 | t6 |  |  |  | G | Design Presentation | E | 6
A | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | >= | 3 | H | Practice | F,G | 2
B | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 10 | >= | 2
C | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 7 | >= | 7
D | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 3 | >= | 3
E | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 7 | >= | 7
F | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 6 | >= | 2
G | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 6 | >= | 6
H | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 2 | >= | 2
Note on H3: =H6
Note on I9: Critical Path A => C => D => E => G => H =SUMPRODUCT($B$6:$H$6,B9:H9)

## Answer Report 1
Microsoft Excel 11.0 Answer Report
Worksheet: [Decision Models Group Project.xls]Finding Critical Path
Report Created: 11/23/2006 1:17:34 PM
Target Cell (Min)
| Cell | Name | Original Value | Final Value
| $H$3 |  | 24 | 28
Adjustable Cells
| Cell | Name | Original Value | Final Value
| $C$6 | t1 | 3 | 3
| $D$6 | t2 | 10 | 10
| $E$6 | t3 | 13 | 13
| $F$6 | t4 | 20 | 20
| $G$6 | t5 | 22 | 26
| $H$6 | t6 | 24 | 28
Constraints
| Cell | Name | Cell Value | Formula | Status | Slack
| $I$12 | A | 3 | $I$12>=$K$12 | Binding | 0
| $I$13 | B | 10 | $I$13>=$K$13 | Not Binding | 8
| $I$14 | C | 7 | $I$14>=$K$14 | Binding | 0
| $I$15 | D | 3 | $I$15>=$K$15 | Binding | 0
| $I$16 | E | 7 | $I$16>=$K$16 | Binding | 0
| $I$17 | F | 6 | $I$17>=$K$17 | Not Binding | 4
| $I$18 | G | 6 | $I$18>=$K$18 | Binding | 0
| $I$19 | H | 2 | $I$19>=$K$19 | Binding | 0

## Crashing Parameters
[7 empty] | 7.5 | [8 empty] | Required activities | Preds. | Duration (hours) | Cost of reducing | Maximum reduction
[15 empty] | A | Planning Meeting |  | 3 | 3.5 | 2
| t0 | t1 | t2 | t3 | t4 | t5 | t6 | [7 empty] | B | Defining objective function and decision variables | A | 2 | 4 | 0.5
| 0 | 3 | 7.5 | 9.4777 | 16.4777 | 22 | 24 | [7 empty] | C | Research | A | 7 | 1.5 | 2.5
[15 empty] | D | Defining constraints | C | 3 | 2.5 | 1.5
| t6: 24 | <== |  | Max Completion Time |  |  |  |  | E | designing model | B,D | 7 | 2.75 | 3
[15 empty] | F | Meeting with Juran | E | 2 | 4 | 0.5
[15 empty] | G | Design Presentation | E | 6 | 2.5 | 3
| t0 | t1 | t2 | t3 | t4 | t5 | t6 |  |  | Improved Duration | Basic Duration | Crash Time | Max Crash | Cost/Time | H | Practice | F,G | 2 | 3 | 1
A | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | >= | 3 | 3 | 0 | 2 | 3.5
B | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 6.4777 | >= | 2 | 2 | 0 | 0.5 | 4 |  | Cost of reducing | Maximum reduction
C | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 4.5 | >= | 4.5 | 7 | 2.5 | 2.5 | 1.5 |  | 3.5 | 2
D | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 1.9777 | >= | 1.9777 | 3 | 1.0223 | 1.5 | 2.5 |  | 4 | 0.5
E | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 7 | >= | 7 | 7 | 0 | 3 | 2.75 |  | 1.5 | 2.5
F | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 5.5223 | >= | 2 | 2 | 0 | 0.5 | 4 |  | 2.5 | 1.5
G | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 5.5223 | >= | 5.5223 | 6 | 0.47769 | 3 | 2.5 |  | 2.75 | 3
H | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 2 | >= | 2 | 2 | 0 | 1 | 3 |  | 4 | 0.5
[16 empty] | 2.5 | 3
[16 empty] | 3 | 1
277.5
360
[13 empty] | 637.5 | 91.0714
642
91.7143
Note on H2: =SUMPRODUCT(N11:N18,P11:P18)
Note on K11: =M12-N12

## Answer Report 2
Microsoft Excel 11.0 Answer Report
Worksheet: [Decision Models Group Project.xls]Crashing Parameters
Report Created: 11/23/2006 2:10:46 PM
Target Cell (Min)
| Cell | Name | Original Value | Final Value
| $H$3 |  | 0 | 7.5
Adjustable Cells
| Cell | Name | Original Value | Final Value
| $C$6 | t1 | 3 | 3
| $D$6 | t2 | 7.5 | 7.5
| $E$6 | t3 | 10.5 | 9.4675
| $F$6 | t4 | 17.5 | 16.4675
| $G$6 | t5 | 22 | 22
| $H$6 | t6 | 24 | 24
| $N$12 | >= Crash Time | 0 | 0
| $N$13 | >= Crash Time | 0 | 0
| $N$14 | >= Crash Time | 0 | 2.5
| $N$15 | >= Crash Time | 0 | 1.0325
| $N$16 | >= Crash Time | 0 | 0
| $N$17 | >= Crash Time | 0 | 0
| $N$18 | >= Crash Time | 0 | 0.4675
| $N$19 | >= Crash Time | 0 | 0
Constraints
| Cell | Name | Cell Value | Formula | Status | Slack
| $I$12 | A <== | 3 | $I$12>=$K$12 | Binding | 0
| $I$13 | B <== | 6.4675 | $I$13>=$K$13 | Not Binding | 4.4675
| $I$14 | C <== | 4.5 | $I$14>=$K$14 | Binding | 0
| $I$15 | D <== | 1.9675 | $I$15>=$K$15 | Binding | 0
| $I$16 | E <== | 7 | $I$16>=$K$16 | Binding | 0
| $I$17 | F <== | 5.5325 | $I$17>=$K$17 | Not Binding | 3.5325
| $I$18 | G <== | 5.5325 | $I$18>=$K$18 | Binding | 0
| $I$19 | H <== | 2 | $I$19>=$K$19 | Binding | 0
| $H$6 | t6 | 24 | $H$6<=$H$8 | Binding | 0
| $N$12 | >= Crash Time | 0 | $N$12<=$O$12 | Not Binding | 2
| $N$13 | >= Crash Time | 0 | $N$13<=$O$13 | Not Binding | 0.5
| $N$14 | >= Crash Time | 2.5 | $N$14<=$O$14 | Binding | 0
| $N$15 | >= Crash Time | 1.0325 | $N$15<=$O$15 | Not Binding | 0.4675
| $N$16 | >= Crash Time | 0 | $N$16<=$O$16 | Not Binding | 3
| $N$17 | >= Crash Time | 0 | $N$17<=$O$17 | Not Binding | 0.5
| $N$18 | >= Crash Time | 0.4675 | $N$18<=$O$18 | Not Binding | 2.5325
| $N$19 | >= Crash Time | 0 | $N$19<=$O$19 | Not Binding | 1

## Sensitivity Report 2
Microsoft Excel 11.0 Sensitivity Report
Worksheet: [Decision Models Group Project.xls]Crashing Parameters
Report Created: 11/23/2006 2:10:46 PM
Adjustable Cells
|  |  | Final | Reduced
| Cell | Name | Value | Gradient
| $C$6 | t1 | 3 | 0
| $D$6 | t2 | 7.5 | 0
| $E$6 | t3 | 9.4675 | 0
| $F$6 | t4 | 16.4675 | 0
| $G$6 | t5 | 22 | 0
| $H$6 | t6 | 24 | -2.5
| $N$12 | >= Crash Time | 0 | 1
| $N$13 | >= Crash Time | 0 | 4
| $N$14 | >= Crash Time | 2.5 | -1
| $N$15 | >= Crash Time | 1.0325 | 0
| $N$16 | >= Crash Time | 0 | 0.25
| $N$17 | >= Crash Time | 0 | 4
| $N$18 | >= Crash Time | 0.4675 | 0
| $N$19 | >= Crash Time | 0 | 0.5
Constraints
|  |  | Final | Lagrange
| Cell | Name | Value | Multiplier
| $I$12 | A <== | 3 | 2.5
| $I$13 | B <== | 6.4675 | 0
| $I$14 | C <== | 4.5 | 2.5
| $I$15 | D <== | 1.9675 | 2.5
| $I$16 | E <== | 7 | 2.5
| $I$17 | F <== | 5.5325 | 0
| $I$18 | G <== | 5.5325 | 2.5
| $I$19 | H <== | 2 | 2.5

## Solver Table
[16 empty] | Required activities | Preds. | Duration (hours) | Cost of reducing | Maximum reduction | Max Completion Time | Reduction in quality
[7 empty] | 7.5 | [7 empty] | A | Planning Meeting |  | 3 | 3.5 | 2 | 14 | Not feasible
[15 empty] | B | Defining objective function and decision variables | A | 2 | 4 | 0.5 | 14.5 | Not feasible
| t0 | t1 | t2 | t3 | t4 | t5 | t6 | [7 empty] | C | Research | A | 7 | 1.5 | 2.5 | 15 | 33.25
| 0 | 3 | 7.5 | 9.4777 | 16.4777 | 22 | 24 | [7 empty] | D | Defining constraints | C | 3 | 2.5 | 1.5 | 15.5 | 31.5
[15 empty] | E | designing model | B,D | 7 | 2.75 | 3 | 16 | 29.75
| t6: 24 | <== |  | Max Completion Time |  |  |  |  | F | Meeting with Juran | E | 2 | 4 | 0.5 | 16.5 | 28
[15 empty] | G | Design Presentation | E | 6 | 2.5 | 3 | 17 | 26.25
[15 empty] | H | Practice | F,G | 2 | 3 | 1 | 17.5 | 24.75
| t0 | t1 | t2 | t3 | t4 | t5 | t6 |  |  | Improved Duration | Basic Duration | Crash Time | Max Crash | Cost/Time | [6 empty] | 18 | 23.25
A | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | >= | 3 | 3 | 0 | 2 | 3.5 |  | Cost of reducing | Maximum reduction |  |  |  | 18.5 | 21.875
B | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 6.4777 | >= | 2 | 2 | 0 | 0.5 | 4 |  | 3.5 | 2 |  |  |  | 19 | 20.5
C | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 4.5 | >= | 4.5 | 7 | 2.5 | 2.5 | 1.5 |  | 4 | 0.5 |  |  |  | 19.5 | 19.125
D | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 1.9777 | >= | 1.9777 | 3 | 1.0223 | 1.5 | 2.5 |  | 1.5 | 2.5 |  |  |  | 20 | 17.75
E | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 7 | >= | 7 | 7 | 0 | 3 | 2.75 |  | 2.5 | 1.5 |  |  |  | 20.5 | 16.375
F | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 5.5223 | >= | 2 | 2 | 0 | 0.5 | 4 |  | 2.75 | 3 |  |  |  | 21 | 15
G | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 5.5223 | >= | 5.5223 | 6 | 0.47769 | 3 | 2.5 |  | 4 | 0.5 |  |  |  | 21.5 | 13.75
H | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 2 | >= | 2 | 2 | 0 | 1 | 3 |  | 2.5 | 3 |  |  |  | 22 | 12.5
[16 empty] | 3 | 1 |  |  |  | 22.5 | 11.25
[21 empty] | 23 | 10
[21 empty] | 23.5 | 8.75
[21 empty] | 24 | 7.5
[21 empty] | 24.5 | 6.25
[21 empty] | 25 | 5
[21 empty] | 25.5 | 3.75
[21 empty] | 26 | 3
[21 empty] | 26.5 | 2.25
[21 empty] | 27 | 1.5
[21 empty] | 27.5 | 0.75
[21 empty] | 28 | 0
[21 empty] | 28.5 | 0

## Sensitivity Report 1
Microsoft Excel 11.0 Sensitivity Report
Worksheet: [Decision Models Group Project.xls]Finding Critical Path
Report Created: 11/23/2006 1:17:34 PM
Adjustable Cells
|  |  | Final | Reduced
| Cell | Name | Value | Gradient
| $C$6 | t1 | 3 | 0
| $D$6 | t2 | 10 | 0
| $E$6 | t3 | 13 | 0
| $F$6 | t4 | 20 | 0
| $G$6 | t5 | 26 | 0
| $H$6 | t6 | 28 | 0
Constraints
|  |  | Final | Lagrange
| Cell | Name | Value | Multiplier
| $I$12 | A | 3 | 1
| $I$13 | B | 10 | 0
| $I$14 | C | 7 | 1
| $I$15 | D | 3 | 1
| $I$16 | E | 7 | 1
| $I$17 | F | 6 | 0
| $I$18 | G | 6 | 1
| $I$19 | H | 2 | 1

## SolverTableSheet (hidden)
1
$H$8
1
14
28.5
0.5
$H$3
$Z$3