## Slide 1: Project Model Way
Team 16
Jillian Bordeaux
Noa Gershony
Veronica Hsia
Jennifer Huang
Swaroopa Reddy

## Slide 2: The scenario
In the super-nerd MBA Olympics, Columbia and Stern battle it out neck-and-neck for first place.
Only one event remains . . .

## Slide 3: Juran’s modeling competition!
The Rules
Invent a project, design a model, and present it to the board in 24 hours or less.
The Prize
The winning school gets to keep Juran all to themselves -- no more sending emails to one school from another school’s email account!

## Slide 4: The necessary steps
 | Required Activities | Pred. | Duration* (in hours)
A | Planning Meeting |  | 3
B | Define objective function and decision variables | A | 2
C | Research | A | 7
D | Define the constraints | C | 3
E | Design the model | B,D | 7
F | Meet with Juran | E | 2
G | Create the presentation | E | 6
H | Practice the presentation | F,G | 2
* The durations represent the ideal time needed to spend on each step in order to ensure a project of the highest quality, which would receive a perfect grade of 100%.

## Slide 5: Network representation
1
4
2
A
3
C
7
E
7
F
2
6
End
B
2
3
D
3
5
H
2
G
6
0
Start
Planning Meeting
Define objective function, decision variables
Research
Define constraints
Design model
Meet Juran
Create preso
Practice preso

## Slide 6: Run Solver to find the critical path and minimum hours required

## Slide 7: Critical path in blue
1
4
2
A
3
C
7
E
7
F
2
6
End
B
2
3
D
3
5
H
2
G
6
0
Start
Planning Meeting
Define objective function, decision variables
Research
Define constraints
Design model
Meet Juran
Create preso
Practice preso

## Slide 8: Minimum time required is 28 hrs
However, remember that for the competition, we are limited to 24 hours to complete all of these activities.

## Slide 9: All activities can be reduced
 | Required Activities | Points Lost | Max Reduction
A | Planning Meeting | 3.5% | 2
B | Define objective function & decision variables | 4% | 0.5
C | Research | 1.5% | 2.5
D | Define the constraints | 2.5% | 1.5
E | Design the model | 2.75% | 3
F | Meet with Juran | 4% | 0.5
G | Create the presentation | 2.5% | 3
H | Practice the presentation | 3% | 1
Some activities can be reduced more than others.
Reduction of different activities holds varying penalties to the quality of the presentation.

## Slide 10: Run Solver to minimize penalties

## Slide 11: Crashing parameters
Solver concludes that we can still complete the project by crashing certain activities and lose only 7.5%.

## Slide 12: Run Solver Table to see trade-off in quality vs. time
Results

## Slide 13: How optimal quality decreases with less time
7.5 points lost

## Slide 14: The teams’ models
After figuring out the activities that could be crashed while minimizing the amount of points that would be lost, the Stern team completed a model that would have been scored a 92.5%.
The Columbia team, unlike the Stern team, spent too much time emailing their friends on their laptops during class, and failed to minimize their penalties when determining the activities to crash. As a result, they developed a model that would have been scored a 91%.

## Slide 15: Judgment day
Pool of 300 Judges
100 biased judges
(Will assign CBS 4 add’l points)
100 biased judges
(Will assign Stern 1 add’l point)
100 neutral judges
(Will assign points fairly)
Seven judges will be selected at random to judge the competition.

## Slide 16: Judging injustices
Due to the biases, whenever 4 or more of the judges are from Columbia, Columbia will win.
Any other combination of judges will guarantee a Stern victory.
Using Crystal Ball, we determined the probability that 4 or more of the judges would be from Columbia.

## Slide 17: Crystal Ball results
Forecast Cell
Assumption Cells
(1000 trials)

## Slide 18: Crystal Ball setup

## Slide 19: Columbia will (unfairly) win 18% of the time
18%

## Slide 20: In conclusion . . .
Even though there is an 18% chance that, despite all our hard work, Columbia might still unfairly win . . .
We think Juran is worth it.

## Slide 21: Questions?
?