## Slide 1: “Shitty” Decision Model: The Bathroom Access Issue at Stern
Margaret Feinberg, Bradford Stein, Whitney Krueger,
Winston Smith and Ram Mohan

## Slide 2: Bathroom Cleanliness vs Bathroom Availability
Follies 2013 Video
Stern students running into bathrooms blocked off due to cleaning
Often during peak times such as passing periods:
    10:20a to 10:30a
    11:50a to 12:00p
    1:20p to 1:30p
    2:50p to 3:00p
    4:20p to 4:30p
Goal: Keep bathrooms open during passing periods

## Slide 3: The Issue: Student Perspective
Bathrooms are ALWAYS being cleaned when we need them most
When blocked from one bathroom, students need to find another which is often 100% utilized because of capacity reduction.
Sent on time wasting search for an open bathroom
With only 10 minutes available until the next class or meeting, students are forced to sit in class or meeting with discomfort

## Slide 4: The Issue: Administration Perspective
Additional cleaning service implemented to as a response to complaints of bathrooms being TOO DIRTY
Stern must use Collins Building Services Inc. (CBS) as cleaning service due to NYU wide contract
  Liability
  Scale
CBS uses union labor and sets requirements for:
  Number of hours per shift
  Time of day
  Day of the week
  Requirements raise the expense and lock in additional constraints

## Slide 5: Cleaning Data
Stern took on an additional cleaning contract to deep clean each bathroom twice per day to address complaints of dirty bathrooms
Current contract began in August 2013 and extends to May 2014
Cost $29,693.66 per month
$296,936.60 for 10 month period

## Slide 6: Cleaning Data
28 bathrooms that get shutdown for cleaning twice per day Monday-Friday
Two Shifts
  10:00am to 1:30pm
  2:3pm to 6:00pm
Four Total Cleaning Staff: two women, two men
Utilize one cleaning staff per bathroom. Therefore, four bathrooms shutdown at a time.
Only one bathroom closed per floor at a time

## Slide 7: Cleaning Procedures

## Slide 8: Solving the Issue
Objective
  Determine cost to reduce bathroom cleaning time to fit the student schedule while still delivering on service level
Decision Variables
  Nodes in diagram represent discrete events/activities, corresponding to the completion times of the various activities.
  Problem is which activities to “crash” and by how much in order to minimize cleaning times
Considerations
  Contractor
  # of hours per shift/week per janitorial employee
  Basic level of cleanliness
  Sequential order in which bathrooms are cleaned
  Each activity has a fixed duration
  There are precedence relationships among cleaning activities

## Slide 9: Cleaning Tasks & Duration Assumptions
Symbol | Task | Duration (mins)
A | Assemble equipment, including gloves, goggles and dispenser keys | 1
B | Knock and announce "service," place "caution" sign, place door stop | 1
C | Check vents and ledges and clean | 1.5
D | Dust mop or sweep out corners and floors | 2
E | Apply product to interior of urinals and bowls using bowl mop | 1.5
F | Let product work 5-10 minutes | 10
G | Spray exterior of urinals and bowls, chrome and immediate floor area | 1.5
H | Give product time to work, 5-10 minutes | 10
I | Clean mirrors | 1.5
J | Clean sinks, countertops and faucets. | 2
K | Wait 5 minutes and wipe sinks, countertops and faucets dry | 5
L | Re-stock and refill dispensers. Paper towel, toilet paper, hand soap and sanitary products | 3
M | Wipe down all dispensers | 2
N | Clean wall partitions, light switches, push and kick plates with clean cloth | 1
O | Spot clean walls | 2
P | Empty and clean trash and sanitary receptacles | 1.5
Q | Damp mop floors working from corner out to door | 3
R | Clean interior of bowls and urinals using bowl mop | 1.5
S | Tie up old trash liners | 1
T | Clean exterior of bowls and urinals with a clean dry cloth | 1.5
U | Insert new liner | 1
V | Inspect area for quality control and damage | 1
W | Pick-up "wet floor sign" and door stop when floor is dry and turn lights off | 1
X | Return and restock cart | 1.5

## Slide 10
A
1
B
1
C
1.5
D
2
2
1
3
4
5
6
7
9
E
1.5
F 10
G 1.5
R
1.5
I
1.5
8
H 10
T
1.5
J 2
10
L 3
K 5
11
12
13
14
15
16
17
18
19
20
M 2
N 1
O 2
P 1.5
Q 3
S 1
U 1
V 1
W 1
X 1.5
END
21
0
Key
Letter: Activity Symbol
Number: Duration
Critical Path
Non-Critical
F 10

## Slide 11: Basic Solver Solution
t0 | t1 | t2 | t3 | t4 | t5 | t6 | t7 | t8 | t9 | t10 | t11 | t12 | t13 | t14 | t15 | t16 | t17 | t18 | t19 | t20 | t21 | 
0 | 1 | 2 | 3.5 | 5.5 | 7 | 17 | 8.5 | 23 | 10 | 12 | 15 | 17 | 18 | 20 | 21.5 | 24.5 | 25.5 | 26.5 | 27.5 | 28.5 | 30 | Total Minutes

## Slide 12: Answer Report
Constraints |  |  |  |  |  | 
 | Cell | Name | Cell Value | Formula | Status | Slack
 | $X$10 | A Total | 1 | $X$10>=$Z$10 | Binding | 0
 | $X$11 | B Total | 1 | $X$11>=$Z$11 | Binding | 0
 | $X$12 | C Total | 1.5 | $X$12>=$Z$12 | Binding | 0
 | $X$13 | D Total | 2 | $X$13>=$Z$13 | Binding | 0
 | $X$14 | E Total | 1.5 | $X$14>=$Z$14 | Binding | 0
 | $X$15 | F Total | 10 | $X$15>=$Z$15 | Binding | 0
 | $X$16 | G Total | 1.5 | $X$16>=$Z$16 | Binding | 0
 | $X$17 | H Total | 14.5 | $X$17>=$Z$17 | Not Binding | 4.5
 | $X$18 | I Total | 1.5 | $X$18>=$Z$18 | Binding | 0
 | $X$19 | J Total | 2 | $X$19>=$Z$19 | Binding | 0
 | $X$20 | K Total | 12.5 | $X$20>=$Z$20 | Not Binding | 7.5
 | $X$21 | L Total | 3 | $X$21>=$Z$21 | Binding | 0
 | $X$22 | M Total | 2 | $X$22>=$Z$22 | Binding | 0
 | $X$23 | N Total | 1 | $X$23>=$Z$23 | Binding | 0
 | $X$24 | O Total | 2 | $X$24>=$Z$24 | Binding | 0
 | $X$25 | P Total | 1.5 | $X$25>=$Z$25 | Binding | 0
 | $X$26 | Q Total | 3 | $X$26>=$Z$26 | Binding | 0
 | $X$27 | R Total | 7.5 | $X$27>=$Z$27 | Not Binding | 6
 | $X$28 | S Total | 1 | $X$28>=$Z$28 | Binding | 0
 | $X$29 | T Total | 1.5 | $X$29>=$Z$29 | Binding | 0
 | $X$30 | U Total | 1 | $X$30>=$Z$30 | Binding | 0
 | $X$31 | V Total | 1 | $X$31>=$Z$31 | Binding | 0
 | $X$32 | W Total | 1 | $X$32>=$Z$32 | Binding | 0
 | $X$33 | X Total | 1.5 | $X$33>=$Z$33 | Binding | 0

## Slide 13: Crashing
Using Solver, we determined that the optimal cleaning sequence without crashing takes 30 minutes per bathroom
  Total of 1680 minutes of cleaning per day
What if cut the breaks out of each shift so that no cleaning would occur?
  Shift 1: 10:30 AM to 11:50 AM  80 minutes
  Shift 2: 12:00 PM to 1:30 PM  90 minutes
  Shift 3: 3:00 PM to 4:20 PM  80 minutes
  Shift 4: 5:00 PM to 6:00 PM  60 minutes
    New Total: 1240 minutes available for cleaning
    Would need to crash 440 minutes throughout the day to make this work
    That’s roughly 15.7 minutes per bathroom per day, 7.9 minutes per cleaning
    Target: improved bathroom cleaning duration: 22.14 minutes

## Slide 14: Crashing

## Slide 15: Cost of Attendance Data
Annual Stern Tuition: $61,274 ($30,637/semester)
15 credits per semester, 15 weeks per semester
Cost per credit hour: $136.16
Average salary foregone per hour: $28.85
Total Cost of MBA per minute: $2.75
The MBA Expense |  |  |  | 
Tuition and Fees | $61,274.00 |  | Average Pre-MBA Salary (Opportunity Cost) | $60,000.00
Months in academic calendar | 9 |  | 9 Month Average Salary Forgeone | $45,000.00
Semesters | 2 |  | Weeks in 3/4 Year | 39
Credits per semester | 15 |  | Hours Worked (40 hour work week) | 1560
Weeks per Semester | 15 |  | Salary Foregone per Hour | $28.85
Credit Hours | 225 |  |  | 
Tuition for 1 semester | $30,637.00 |  |  | 
Tuition per Credit Hour | $136.16 |  |  | 
Total cost of 1 hour of MBA's time | $165.01 |  |  | 
Total cost of 1 minute of MBA time | $2.75 |  |  | 

## Slide 16: When you include the value of an MBA’s Time…
To crash the cleaning of the bathrooms in order to avoid conflicts during breaks would cost:
  10 months * 4 weeks per month * 5 days per week * $393.34 per day to crash bathrooms = $78,668 per year
Compare that to the value of students’ lost time when they cannot use the bathrooms:
  Assume 75% of 800 MBA full-time students are in the building during class time
  Diversion rate = 10 % per break
  60 students diverted for approx. 1 minute per break
    = 1 hour of lost student time per break
    = $165.10 per break
    5 breaks per day * $165.10 = $825.50 in lost student time per day
    $825.50* 5 days per week * 4 weeks per month * 10 months
      = $165,100

## Slide 17: Conclusion
      $165,100 >$78,668

## Slide 18: Alternative Ideas
Hiring port-a-potties to put in Gould Plaza
  $95 a month, serviced once a week = $1,140
  $29,693.70 /month for 24 bathrooms = $1,237.24 per bathroom
    Equates to $97.24 savings per month per bathroom
Changing sequencing of bathroom cleaning so that most utilized classroom floors (2nd and 3rd) are cleared for peak times between classes and less utilized floor are cleaned instead (e.g. 5th and 6th)
Cut volume/ traffic by banning all undergraduates from using Stern facilities (jk, not really)
Bathroom App

## Slide 19: Questions?....