## Basic
Stern bathroom cleaning: Basic Solver | [23 empty] | 30 | Total Minutes
|  |  | t0 | t1 | t2 | t3 | t4 | t5 | t6 | t7 | t8 | t9 | t10 | t11 | t12 | t13 | t14 | t15 | t16 | t17 | t18 | t19 | t20 | t21
|  |  | 0 | 1 | 2 | 3.5 | 5.5 | 7 | 17 | 8.5 | 23 | 10 | 12 | 15 | 17 | 18 | 20 | 21.5 | 24.5 | 25.5 | 26.5 | 27.5 | 28.5 | 30
Task | t0 | t1 | t2 | t3 | t4 | t5 | t6 | t7 | t8 | t9 | t10 | t11 | t12 | t13 | t14 | t15 | t16 | t17 | t18 | t19 | t20 | t21 | Total |  | Duration
A | [22 empty] | 1 | >= | 1 | bar: t0 to t1
B | [22 empty] | 1 | >= | 1 | bar: t1 to t2
C | [22 empty] | 1.5 | >= | 1.5 | bar: t2 to t3
D | [22 empty] | 2 | >= | 2 | bar: t3 to t4
E | [22 empty] | 1.5 | >= | 1.5 | bar: t4 to t5
F | [22 empty] | 10 | >= | 10 | bar: t5 to t6
G | t5: -1; t6: 0; t7: 1 | 1.5 | >= | 1.5
H | [22 empty] | 14.5 | >= | 10 | bar: t7 to t8
I | t7: -1; t8: 0; t9: 1 | 1.5 | >= | 1.5
J | [22 empty] | 2 | >= | 2 | bar: t9 to t10
K | t10: -1; t11: 0; t12: 0; t13: 0; t14: 0; t15: 0; t16: 1 | 12.5 | >= | 5
L | [22 empty] | 3 | >= | 3 | bar: t10 to t11
M | [22 empty] | 2 | >= | 2 | bar: t11 to t12
N | [22 empty] | 1 | >= | 1 | bar: t12 to t13
O | [22 empty] | 2 | >= | 2 | bar: t13 to t14
P | [22 empty] | 1.5 | >= | 1.5 | bar: t14 to t15
Q | [22 empty] | 3 | >= | 3 | bar: t15 to t16
R | t6: -1; t7: 0; t8: 0; t9: 0; t10: 0; t11: 0; t12: 0; t13: 0; t14: 0; t15: 0; t16: 1 | 7.5 | >= | 1.5
S | [22 empty] | 1 | >= | 1 | bar: t16 to t17
T | t8: -1; t9: 0; t10: 0; t11: 0; t12: 0; t13: 0; t14: 0; t15: 0; t16: 1 | 1.5 | >= | 1.5
U | [22 empty] | 1 | >= | 1 | bar: t17 to t18
V | [22 empty] | 1 | >= | 1 | bar: t18 to t19
W | [22 empty] | 1 | >= | 1 | bar: t19 to t20
X | [22 empty] | 1.5 | >= | 1.5 | bar: t20 to t21

## Basic Answer Report
Microsoft Excel 14.3 Answer Report
Worksheet: [dec models final proj v2.xlsx]Basic
Report Created: 12/6/2013 2:31:37 PM
Result: Solver found a solution. All constraints and optimality conditions are satisfied.
Solver Engine
Engine: Simplex LP
Solution Time: 1.092349 Seconds.
Iterations: 26 Subproblems: 0
Solver Options
Max Time Unlimited, Iterations Unlimited, Precision 0.000001, Use Automatic Scaling
Max Subproblems Unlimited, Max Integer Sols Unlimited, Integer Tolerance 1%, Assume NonNegative
Objective Cell (Min)
| Cell | Name | Original Value | Final Value
| $AB$4 | Total Minutes | 30 | 30
Variable Cells
| Cell | Name | Original Value | Final Value | Integer
| $E$4 | t1 | 1 | 1 | Contin
| $F$4 | t2 | 2 | 2 | Contin
| $G$4 | t3 | 3.5 | 3.5 | Contin
| $H$4 | t4 | 5.5 | 5.5 | Contin
| $I$4 | t5 | 7 | 7 | Contin
| $J$4 | t6 | 17 | 17 | Contin
| $K$4 | t7 | 8.5 | 8.5 | Contin
| $L$4 | t8 | 23 | 23 | Contin
| $M$4 | t9 | 10 | 10 | Contin
| $N$4 | t10 | 12 | 12 | Contin
| $O$4 | t11 | 15 | 15 | Contin
| $P$4 | t12 | 17 | 17 | Contin
| $Q$4 | t13 | 18 | 18 | Contin
| $R$4 | t14 | 20 | 20 | Contin
| $S$4 | t15 | 21.5 | 21.5 | Contin
| $T$4 | t16 | 24.5 | 24.5 | Contin
| $U$4 | t17 | 25.5 | 25.5 | Contin
| $V$4 | t18 | 26.5 | 26.5 | Contin
| $W$4 | t19 | 27.5 | 27.5 | Contin
| $X$4 | t20 | 28.5 | 28.5 | Contin
| $Y$4 | t21 | 30 | 30 | Contin
Constraints
| Cell | Name | Cell Value | Formula | Status | Slack
| $X$10 | A Total | 1 | $X$10>=$Z$10 | Binding | 0
| $X$11 | B Total | 1 | $X$11>=$Z$11 | Binding | 0
| $X$12 | C Total | 1.5 | $X$12>=$Z$12 | Binding | 0
| $X$13 | D Total | 2 | $X$13>=$Z$13 | Binding | 0
| $X$14 | E Total | 1.5 | $X$14>=$Z$14 | Binding | 0
| $X$15 | F Total | 10 | $X$15>=$Z$15 | Binding | 0
| $X$16 | G Total | 1.5 | $X$16>=$Z$16 | Binding | 0
| $X$17 | H Total | 14.5 | $X$17>=$Z$17 | Not Binding | 4.5
| $X$18 | I Total | 1.5 | $X$18>=$Z$18 | Binding | 0
| $X$19 | J Total | 2 | $X$19>=$Z$19 | Binding | 0
| $X$20 | K Total | 12.5 | $X$20>=$Z$20 | Not Binding | 7.5
| $X$21 | L Total | 3 | $X$21>=$Z$21 | Binding | 0
| $X$22 | M Total | 2 | $X$22>=$Z$22 | Binding | 0
| $X$23 | N Total | 1 | $X$23>=$Z$23 | Binding | 0
| $X$24 | O Total | 2 | $X$24>=$Z$24 | Binding | 0
| $X$25 | P Total | 1.5 | $X$25>=$Z$25 | Binding | 0
| $X$26 | Q Total | 3 | $X$26>=$Z$26 | Binding | 0
| $X$27 | R Total | 7.5 | $X$27>=$Z$27 | Not Binding | 6
| $X$28 | S Total | 1 | $X$28>=$Z$28 | Binding | 0
| $X$29 | T Total | 1.5 | $X$29>=$Z$29 | Binding | 0
| $X$30 | U Total | 1 | $X$30>=$Z$30 | Binding | 0
| $X$31 | V Total | 1 | $X$31>=$Z$31 | Binding | 0
| $X$32 | W Total | 1 | $X$32>=$Z$32 | Binding | 0
| $X$33 | X Total | 1.5 | $X$33>=$Z$33 | Binding | 0

## Crashing
Stern bathroom cleaning: Crashing
|  |  | t0 | t1 | t2 | t3 | t4 | t5 | t6 | t7 | t8 | t9 | t10 | t11 | t12 | t13 | t14 | t15 | t16 | t17 | t18 | t19 | t20 | t21
|  |  | 0 | 1 | 2 | 2.75 | 3.75 | 5.25 | 16.75 | 6.75 | 16.75 | 7.5 | 8.5 | 10 | 11 | 11.75 | 13.75 | 15.25 | 18.25 | 18.75 | 19.64 | 20.14 | 20.64 | 22.14 |  | 7.024
[26 empty] | total per day | 393.344
[19 empty] | t24 | <= | 22.14 | <-- | Max Completion Time
Task | t0 | t1 | t2 | t3 | t4 | t5 | t6 | t7 | t8 | t9 | t10 | t11 | t12 | t13 | t14 | t15 | t16 | t17 | t18 | t19 | t20 | t21 | Total |  | Improved Duration | Basic Duration | Crash Time | Max Crash | Cost/Time
A | [22 empty] | 1 | >= | 1 | 1 | 0 | 0 | 5 | bar: t0 to t1
B | [22 empty] | 1 | >= | 1 | 1 | 0 | 0.5 | 2 | bar: t1 to t2
C | [22 empty] | 0.75 | >= | 0.75 | 1.5 | 0.75 | 0.75 | 1 | bar: t2 to t3
D | [22 empty] | 1 | >= | 1 | 2 | 1 | 1 | 0.5 | bar: t3 to t4
E | [22 empty] | 1.5 | >= | 1.5 | 1.5 | 0 | 0.75 | 3 | bar: t4 to t5
F | [22 empty] | 11.5 | >= | 10 | 10 | 0 | 0 | 0 | bar: t5 to t6
G | t5: -1; t6: 0; t7: 1 | 1.5 | >= | 1.5 | 1.5 | 0 | 0.75 | 3.75
H | [22 empty] | 10 | >= | 10 | 10 | 0 | 0 | 0 | bar: t7 to t8
I | t7: -1; t8: 0; t9: 1 | 0.75 | >= | 0.75 | 1.5 | 0.75 | 0.75 | 0.8
J | [22 empty] | 1 | >= | 1 | 2 | 1 | 1 | 0.66 | bar: t9 to t10
K | [22 empty] | 9.75 | >= | 5 | 5 | 0 | 0 | 0 | bar: t10; t16
L | [22 empty] | 1.5 | >= | 1.5 | 3 | 1.5 | 1.5 | 1.1 | bar: t10 to t11
M | [22 empty] | 1 | >= | 1 | 2 | 1 | 1 | 0.9 | bar: t11 to t12
N | [22 empty] | 0.75 | >= | 0.75 | 1 | 0.25 | 0.5 | 1.3 | bar: t12 to t13
O | [22 empty] | 2 | >= | 2 | 2 | 0 | 1 | 1.7 | bar: t13 to t14
P | [22 empty] | 1.5 | >= | 1.5 | 1.5 | 0 | 0.75 | 2.1 | bar: t14 to t15
Q | [22 empty] | 3 | >= | 3 | 3 | 0 | 1.5 | 1.9 | bar: t15 to t16
R | [22 empty] | 1.5 | >= | 1.5 | 1.5 | 0 | 0.75 | 4 | bar: t6; t16
S | [22 empty] | 0.5 | >= | 0.5 | 1 | 0.5 | 0.5 | 0.99 | bar: t16 to t17
T | [22 empty] | 1.5 | >= | 1.5 | 1.5 | 0 | 0.75 | 0.97 | bar: t8; t16
U | [22 empty] | 0.89 | >= | 0.89 | 1 | 0.11 | 0.5 | 1.4 | bar: t17 to t24 t18
V | [22 empty] | 0.5 | >= | 0.5 | 1 | 0.5 | 0.5 | 1.2 | bar: t24 t18 to <= t19
W | [22 empty] | 0.5 | >= | 0.5 | 1 | 0.5 | 0.5 | 0.78 | bar: <= t19 to 22.14 t20
X | [22 empty] | 1.5 | >= | 1.5 | 1.5 | 0 | 0 | 2.1 | bar: 22.14 t20 to <-- t21
Note on AB4: Cost to crash each cleaning session = sumproduct(AF10:AF33,AH10:AH33)
Note on AC5: Cost to crash all the bathroom cleanings per day = AE*28*2
Note on V7: 30 minutes minus 7.86
Note on AD9: Crashed each activity that could be done by 2 people by cutting time in half
Note on AE9: - $29,693.7 per month for cleaning - Divided by 20 for 5 days a week, 4 weeks per month: = $1484.68 per day - Divided by 1680 minutes worked by 4 workers per day = $0.88 cost per minute

## Answer Report 2
Microsoft Excel 14.3 Answer Report
Worksheet: [dec models final proj v2.xlsx]Crashing
Report Created: 12/5/2013 7:13:48 PM
Result: Solver found a solution. All constraints and optimality conditions are satisfied.
Solver Engine
Engine: Simplex LP
Solution Time: 1.637596 Seconds.
Iterations: 33 Subproblems: 0
Solver Options
Max Time Unlimited , Iterations Unlimited , Precision 0.000001
Max Subproblems Unlimited , Max Integer Sols Unlimited , Integer Tolerance 1%, Solve Without Integer Constraints , Assume NonNegative
Objective Cell (Min)
| Cell | Name | Original Value | Final Value
| $AE$4 |  | 5.0373 | 6.9462
Variable Cells
| Cell | Name | Original Value | Final Value | Integer
| $E$4 | t1 | 1 | 1 | Contin
| $F$4 | t2 | 1.5 | 1.5 | Contin
| $G$4 | t3 | 2.25 | 2.25 | Contin
| $H$4 | t4 | 3.25 | 3.25 | Contin
| $I$4 | t5 | 4 | 4 | Contin
| $J$4 | t6 | 14 | 14 | Contin
| $K$4 | t7 | 15.5 | 15.5 | Contin
| $L$4 | t8 | 4.75 | 4.75 | Contin
| $M$4 | t9 | 14.75 | 14.75 | Contin
| $N$4 | t10 | 16.25 | 16.25 | Contin
| $O$4 | t11 | 5.5 | 5.5 | Contin
| $P$4 | t12 | 6.5 | 6.5 | Contin
| $Q$4 | t13 | 11.5 | 11.5 | Contin
| $R$4 | t14 | 9.3 | 8 | Contin
| $S$4 | t15 | 11.3 | 9.14 | Contin
| $T$4 | t16 | 12.3 | 10.14 | Contin
| $U$4 | t17 | 14.3 | 12.14 | Contin
| $V$4 | t18 | 15.8 | 13.64 | Contin
| $W$4 | t19 | 18.8 | 16.64 | Contin
| $X$4 | t20 | 19.8 | 17.64 | Contin
| $Y$4 | t21 | 20.8 | 18.64 | Contin
| $Z$4 | t22 | 21.8 | 19.64 | Contin
| $AA$4 | t23 | 22.8 | 20.64 | Contin
| $AB$4 | t24 | 24.3 | 22.14 | Contin
| $AF$10 | >= Crash Time | 0 | 0 | Contin
| $AF$11 | >= Crash Time | 0.5 | 0.5 | Contin
| $AF$12 | >= Crash Time | 0.75 | 0.75 | Contin
| $AF$13 | >= Crash Time | 1 | 1 | Contin
| $AF$14 | >= Crash Time | 0.75 | 0.75 | Contin
| $AF$15 | >= Crash Time | 0 | 0 | Contin
| $AF$16 | >= Crash Time | 0.75 | 0.75 | Contin
| $AF$17 | >= Crash Time | 0 | 0 | Contin
| $AF$18 | >= Crash Time | 0.75 | 0.75 | Contin
| $AF$19 | >= Crash Time | 1 | 1 | Contin
| $AF$20 | >= Crash Time | 0 | 0 | Contin
| $AF$21 | >= Crash Time | 0.2 | 1.5 | Contin
| $AF$22 | >= Crash Time | 0 | 0.86 | Contin
| $AF$23 | >= Crash Time | 0 | 0 | Contin
| $AF$24 | >= Crash Time | 0 | 0 | Contin
| $AF$25 | >= Crash Time | 0 | 0 | Contin
| $AF$26 | >= Crash Time | 0 | 0 | Contin
| $AF$27 | >= Crash Time | 0 | 0 | Contin
| $AF$28 | >= Crash Time | 0 | 0 | Contin
| $AF$29 | >= Crash Time | 0 | 0 | Contin
| $AF$30 | >= Crash Time | 0 | 0 | Contin
| $AF$31 | >= Crash Time | 0 | 0 | Contin
| $AF$32 | >= Crash Time | 0 | 0 | Contin
| $AF$33 | >= Crash Time | 0 | 0 | Contin
Constraints
| Cell | Name | Cell Value | Formula | Status | Slack
| $AA$10 | A Total | 1 | $AA$10>=$AC$10 | Binding | 0
| $AA$11 | B Total | 0.5 | $AA$11>=$AC$11 | Binding | 0
| $AA$12 | C Total | 0.75 | $AA$12>=$AC$12 | Binding | 0
| $AA$13 | D Total | 1 | $AA$13>=$AC$13 | Binding | 0
| $AA$14 | E Total | 0.75 | $AA$14>=$AC$14 | Binding | 0
| $AA$15 | F Total | 10 | $AA$15>=$AC$15 | Binding | 0
| $AA$16 | G Total | 0.75 | $AA$16>=$AC$16 | Binding | 0
| $AA$17 | H Total | 10 | $AA$17>=$AC$17 | Binding | 0
| $AA$18 | I Total | 0.75 | $AA$18>=$AC$18 | Binding | 0
| $AA$19 | J Total | 1 | $AA$19>=$AC$19 | Binding | 0
| $AA$20 | K Total | 5 | $AA$20>=$AC$20 | Binding | 0
| $AA$21 | L Total | 1.5 | $AA$21>=$AC$21 | Binding | 0
| $AA$22 | M Total | 1.14 | $AA$22>=$AC$22 | Binding | 0
| $AA$23 | N Total | 1 | $AA$23>=$AC$23 | Binding | 0
| $AA$24 | O Total | 2 | $AA$24>=$AC$24 | Binding | 0
| $AA$25 | P Total | 1.5 | $AA$25>=$AC$25 | Binding | 0
| $AA$26 | Q Total | 3 | $AA$26>=$AC$26 | Binding | 0
| $AA$27 | R Total | 1.5 | $AA$27>=$AC$27 | Binding | 0
| $AA$28 | S Total | 1 | $AA$28>=$AC$28 | Binding | 0
| $AA$29 | T Total | 1.5 | $AA$29>=$AC$29 | Binding | 0
| $AA$30 | U Total | 1 | $AA$30>=$AC$30 | Binding | 0
| $AA$31 | V Total | 1 | $AA$31>=$AC$31 | Binding | 0
| $AA$32 | W Total | 1 | $AA$32>=$AC$32 | Binding | 0
| $AA$33 | X Total | 1.5 | $AA$33>=$AC$33 | Binding | 0
| $AB$4 | t24 | 22.14 | $AB$4<=$AB$7 | Binding | 0
| $AF$10 | >= Crash Time | 0 | $AF$10<=$AG$10 | Binding | 0
| $AF$11 | >= Crash Time | 0.5 | $AF$11<=$AG$11 | Binding | 0
| $AF$12 | >= Crash Time | 0.75 | $AF$12<=$AG$12 | Binding | 0
| $AF$13 | >= Crash Time | 1 | $AF$13<=$AG$13 | Binding | 0
| $AF$14 | >= Crash Time | 0.75 | $AF$14<=$AG$14 | Binding | 0
| $AF$15 | >= Crash Time | 0 | $AF$15<=$AG$15 | Binding | 0
| $AF$16 | >= Crash Time | 0.75 | $AF$16<=$AG$16 | Binding | 0
| $AF$17 | >= Crash Time | 0 | $AF$17<=$AG$17 | Binding | 0
| $AF$18 | >= Crash Time | 0.75 | $AF$18<=$AG$18 | Binding | 0
| $AF$19 | >= Crash Time | 1 | $AF$19<=$AG$19 | Binding | 0
| $AF$20 | >= Crash Time | 0 | $AF$20<=$AG$20 | Binding | 0
| $AF$21 | >= Crash Time | 1.5 | $AF$21<=$AG$21 | Binding | 0
| $AF$22 | >= Crash Time | 0.86 | $AF$22<=$AG$22 | Not Binding | 0.14
| $AF$23 | >= Crash Time | 0 | $AF$23<=$AG$23 | Not Binding | 0.5
| $AF$24 | >= Crash Time | 0 | $AF$24<=$AG$24 | Not Binding | 1
| $AF$25 | >= Crash Time | 0 | $AF$25<=$AG$25 | Not Binding | 0.75
| $AF$26 | >= Crash Time | 0 | $AF$26<=$AG$26 | Not Binding | 1.5
| $AF$27 | >= Crash Time | 0 | $AF$27<=$AG$27 | Not Binding | 0.75
| $AF$28 | >= Crash Time | 0 | $AF$28<=$AG$28 | Not Binding | 0.5
| $AF$29 | >= Crash Time | 0 | $AF$29<=$AG$29 | Not Binding | 0.75
| $AF$30 | >= Crash Time | 0 | $AF$30<=$AG$30 | Not Binding | 0.5
| $AF$31 | >= Crash Time | 0 | $AF$31<=$AG$31 | Not Binding | 0.5
| $AF$32 | >= Crash Time | 0 | $AF$32<=$AG$32 | Not Binding | 0.5
| $AF$33 | >= Crash Time | 0 | $AF$33<=$AG$33 | Binding | 0

## Sheet7
Stern tuition | 61274
Average S
To count as three Stern credits, a course must meet at least 36 hours. To count as 1.5 Stern credits, a course must meet at least 18 hours.
180 | one semester hours
360 | two semesters hours
170.2056 | cost per hour
2.8368 | cost per minute that students pay