## Model
Activity | Description | Predecessors | Start Node | End Node | Min | Alpha | Beta | Scale | CB Time | Simulated Time | Start Time | End Time | Critical?
A | Survey Site | None | 0 | 1 | 2 | 4 | 4 | 2 | 3 | 5 | 0 | 5 | 1
B | Excavation | A | 1 | 2 | 9 | 4 | 4 | 6 | 12 | 21 | 5 | 26 | 1
C | Prepare Drawings | None | 0 | 3 | 4 | 3.1059 | 4.5675 | 14 | 9.6667 | 13.6667 | 0 | 13.6667 | 0
D | Soil Study | B | 2 | 3 | 1 |  |  | 0 | 1 | 1 | 26 | 27 | 1
E | Prelim. Report | C, D | 3 | 4 | 1 | 4 | 4 | 2 | 2 | 3 | 27 | 30 | 1
F | Approve Plans | E | 4 | 5 | 1 |  |  | 0 | 1 | 1 | 30 | 31 | 1
G | Concrete Forms | F | 5 | 7 | 5 | 2.3333 | 4.6667 | 4 | 6.3333 | 11.3333 | 31 | 42.3333 | 1
H | Procure Steel | F | 5 | 6 | 2 | 3.2292 | 4.5208 | 8 | 5.3333 | 7.3333 | 31 | 38.3333 | 0
I | Order Cement | F | 5 | 8 | 1 |  |  | 0 | 1 | 1 | 31 | 32 | 0
Dummy |  | H | 6 | 8 | 0 |  |  | 0 | 0 | 0 | 38.3333 | 38.3333
J | Deliver Gravel | G | 7 | 8 | 2 | 2.9383 | 4.6173 | 3 | 3.1667 | 5.1667 | 42.3333 | 47.5 | 1
K | Pour Concrete | H, I, J | 8 | 9 | 8 | 2.9383 | 4.6173 | 6 | 10.3333 | 18.3333 | 47.5 | 65.8333 | 1
L | Cure Concrete | K | 9 | 10 | 2 |  |  | 0 | 2 | 2 | 65.8333 | 67.8333 | 1
M | Strength Test | L | 10 | 11 | 2 |  |  | 0 | 2 | 2 | 67.8333 | 69.8333 | 1
Node | Time |  | Path |  |  | Total | Critical?
0 | 0 |  | A-B-D-E-F-H-K-L-M |  |  | 60.6667 | 0
1 | 5 |  | A-C-E-F-H-K-L-M |  |  | 52.3333 | 0
2 | 26 |  | A-B-D-E-F-I-K-L-M |  |  | 54.3333 | 0
3 | 27 |  | A-C-E-F-I-K-L-M |  |  | 46 | 0
4 | 30 |  | A-B-D-E-F-G-J-K-L-M |  |  | 69.8333 | 1
5 | 31 |  | A-C-E-F-G-J-K-L-M |  |  | 61.5 | 0
6 | 38.3333 |  |  |  |  | 69.8333
7 | 42.3333
8 | 47.5
9 | 65.8333
10 | 67.8333 | <= 43? | Penalty
11 | 69.8333 | 0 | 268333.3333

## Model (template)
Activity | Description | Predecessors | Start Node | End Node | Min | Alpha | Beta | Scale | CB Time | Simulated Time | Start Time | End Time | Critical?
A | Survey Site | None | 0 | 1 | 2 | 4 | 4 | 2 | 3 | 5 | 0 | 5 | 1
B | Excavation | A | 1 | 2 | 9 | 4 | 4 | 6 | 12 | 21 | 5 | 26 | 1
C | Prepare Drawings | None | 0 | 3 | 4 | 3.1059 | 4.5675 | 14 | 9.6667 | 13.6667 | 0 | 13.6667 | 0
D | Soil Study | B | 2 | 3 | 1 |  |  | 0 | 1 | 1 | 26 | 27 | 1
E | Prelim. Report | C, D | 3 | 4 | 1 | 4 | 4 | 2 | 2 | 3 | 27 | 30 | 1
F | Approve Plans | E | 4 | 5 | 1 |  |  | 0 | 1 | 1 | 30 | 31 | 1
G | Concrete Forms | F | 5 | 7 | 5 | 2.3333 | 4.6667 | 4 | 6.3333 | 11.3333 | 31 | 42.3333 | 1
H | Procure Steel | F | 5 | 6 | 2 | 3.2292 | 4.5208 | 8 | 5.3333 | 7.3333 | 31 | 38.3333 | 0
I | Order Cement | F | 5 | 8 | 1 |  |  | 0 | 1 | 1 | 31 | 32 | 0
Dummy |  | H | 6 | 8 | 0 |  |  | 0 | 0 | 0 | 38.3333 | 38.3333
J | Deliver Gravel | G | 7 | 8 | 2 | 2.9383 | 4.6173 | 3 | 3.1667 | 5.1667 | 42.3333 | 47.5 | 1
K | Pour Concrete | H, I, J | 8 | 9 | 8 | 2.9383 | 4.6173 | 6 | 10.3333 | 18.3333 | 47.5 | 65.8333 | 1
L | Cure Concrete | K | 9 | 10 | 2 |  |  | 0 | 2 | 2 | 65.8333 | 67.8333 | 1
M | Strength Test | L | 10 | 11 | 2 |  |  | 0 | 2 | 2 | 67.8333 | 69.8333 | 1
Node | Time |  | Path |  |  | Total | Critical?
0 | 0 |  | A-B-D-E-F-H-K-L-M |  |  | 60.6667 | 0
1 | 5 |  | A-C-E-F-H-K-L-M |  |  | 52.3333 | 0
2 | 26 |  | A-B-D-E-F-I-K-L-M |  |  | 54.3333 | 0
3 | 27 |  | A-C-E-F-I-K-L-M |  |  | 46 | 0
4 | 30 |  | A-B-D-E-F-G-J-K-L-M |  |  | 69.8333 | 1
5 | 31 |  | A-C-E-F-G-J-K-L-M |  |  | 61.5 | 0
6 | 38.3333 |  |  |  |  | 69.8333
7 | 42.3333
8 | 47.5
9 | 65.8333
10 | 67.8333 | <= 43? | Penalty
11 | 69.8333 | 0 | 268333.3333

## REPORT
Crystal Ball Report
Simulation started on 6/1/05 at 13:09:57
Simulation stopped on 6/1/05 at 13:09:59
[7 empty] | A-B-D-E-F-H-K-L-M | Frequency | A-C-E-F-H-K-L-M | Frequency | A-B-D-E-F-I-K-L-M | Frequency | A-C-E-F-I-K-L-M | Frequency | A-B-D-E-F-G-J-K-L-M | Frequency | A-C-E-F-G-J-K-L-M | Frequency | A | Frequency | B | Frequency | C | Frequency | D | Frequency | E | Frequency | F | Frequency | G | Frequency | H | Frequency | I | Frequency | J | Frequency | K | Frequency | L | Frequency | M | Frequency | Project Time | Frequency | <= 43? | Frequency | Penalty | Frequency
Forecast: A-B-D-E-F-H-K-L-M | [5 empty] | Cell: H19 | 0.0028469 | 999 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13895 | 0 | 0.029691 | 895 | 1 | 0 | 0.13895 | 0 | 0.029691 | 895 | 0.13895 | 0 | 1 | 0 | 1 | 0 | 0.91744 | 0 | 0.0028469 | 999 | 0 | 0 | 0.91744 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 38.6626 | 7 | 0.033333 | 448 | 1042.146 | 605
[7 empty] | 0.0085408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19833 | 0 | 0.089074 | 0 | 1 | 0 | 0.19833 | 0 | 0.089074 | 0 | 0.19833 | 0 | 1 | 0 | 1 | 0 | 0.92313 | 0 | 0.0085408 | 0 | 0 | 0 | 0.92313 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 39.2548 | 16 | 0.1 | 0 | 3126.4379 | 41
| Summary: | [5 empty] | 0.014235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25771 | 0 | 0.14846 | 0 | 1 | 0 | 0.25771 | 0 | 0.14846 | 0 | 0.25771 | 0 | 1 | 0 | 1 | 0 | 0.92883 | 0 | 0.014235 | 0 | 0 | 0 | 0.92883 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 39.8471 | 32 | 0.16667 | 0 | 5210.7299 | 36
|  | Display Range is from 0.0000 to 0.0854 |  |  |  |  | 0.019928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3171 | 0 | 0.20784 | 0 | 1 | 0 | 0.3171 | 0 | 0.20784 | 0 | 0.3171 | 0 | 1 | 0 | 1 | 0 | 0.93452 | 0 | 0.019928 | 0 | 0 | 0 | 0.93452 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 40.4394 | 35 | 0.23333 | 0 | 7295.0219 | 36
|  | Entire Range is from 0.0000 to 1.0000 |  |  |  |  | 0.025622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37648 | 0 | 0.26722 | 0 | 1 | 0 | 0.37648 | 0 | 0.26722 | 0 | 0.37648 | 0 | 1 | 0 | 1 | 0 | 0.94021 | 0 | 0.025622 | 0 | 0 | 0 | 0.94021 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 41.0316 | 83 | 0.3 | 0 | 9379.3138 | 34
|  | After 1,000 Trials, the Std. Error of the Mean is 0.0010 |  |  |  |  | 0.031316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43586 | 0 | 0.32661 | 0 | 1 | 0 | 0.43586 | 0 | 0.32661 | 0 | 0.43586 | 0 | 1 | 0 | 1 | 0 | 0.94591 | 0 | 0.031316 | 0 | 0 | 0 | 0.94591 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 41.6239 | 124 | 0.36667 | 0 | 11463.6058 | 35
[7 empty] | 0.03701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49525 | 0 | 0.38599 | 0 | 1 | 0 | 0.49525 | 0 | 0.38599 | 0 | 0.49525 | 0 | 1 | 0 | 1 | 0 | 0.9516 | 0 | 0.03701 | 0 | 0 | 0 | 0.9516 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 42.2162 | 141 | 0.43333 | 0 | 13547.8978 | 27
| Statistics: |  |  |  | Value |  | 0.042704 | 0 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0.55463 | 0 | 0.44537 | 0 | 1 | 1000 | 0.55463 | 0 | 0.44537 | 0 | 0.55463 | 0 | 1 | 1000 | 1 | 1000 | 0.9573 | 0 | 0.042704 | 0 | 0 | 1000 | 0.9573 | 0 | 1 | 1000 | 1 | 1000 | 1 | 1000 | 42.8084 | 136 | 0.5 | 0 | 15632.1897 | 27
|  | Trials |  |  | 1000 |  | 0.048398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61401 | 0 | 0.50475 | 0 | 1 | 0 | 0.61401 | 0 | 0.50475 | 0 | 0.61401 | 0 | 1 | 0 | 1 | 0 | 0.96299 | 0 | 0.048398 | 0 | 0 | 0 | 0.96299 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 43.4007 | 113 | 0.56667 | 0 | 17716.4817 | 30
|  | Mean |  |  | 0.001 |  | 0.054092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67339 | 0 | 0.56414 | 0 | 1 | 0 | 0.67339 | 0 | 0.56414 | 0 | 0.67339 | 0 | 1 | 0 | 1 | 0 | 0.96868 | 0 | 0.054092 | 0 | 0 | 0 | 0.96868 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 43.993 | 103 | 0.63333 | 0 | 19800.7737 | 20
|  | Median |  |  | 0 |  | 0.059785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73278 | 0 | 0.62352 | 0 | 1 | 0 | 0.73278 | 0 | 0.62352 | 0 | 0.73278 | 0 | 1 | 0 | 1 | 0 | 0.97438 | 0 | 0.059785 | 0 | 0 | 0 | 0.97438 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 44.5852 | 77 | 0.7 | 0 | 21885.0656 | 27
|  | Mode |  |  | 0 |  | 0.065479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.79216 | 0 | 0.6829 | 0 | 1 | 0 | 0.79216 | 0 | 0.6829 | 0 | 0.79216 | 0 | 1 | 0 | 1 | 0 | 0.98007 | 0 | 0.065479 | 0 | 0 | 0 | 0.98007 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 45.1775 | 67 | 0.76667 | 0 | 23969.3576 | 22
|  | Standard Deviation |  |  | 0.031623 |  | 0.071173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85154 | 0 | 0.74229 | 0 | 1 | 0 | 0.85154 | 0 | 0.74229 | 0 | 0.85154 | 0 | 1 | 0 | 1 | 0 | 0.98577 | 0 | 0.071173 | 0 | 0 | 0 | 0.98577 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 45.7698 | 25 | 0.83333 | 0 | 26053.6496 | 13
|  | Variance |  |  | 0.001 |  | 0.076867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91093 | 0 | 0.80167 | 0 | 1 | 0 | 0.91093 | 0 | 0.80167 | 0 | 0.91093 | 0 | 1 | 0 | 1 | 0 | 0.99146 | 0 | 0.076867 | 0 | 0 | 0 | 0.99146 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 46.362 | 18 | 0.9 | 0 | 28137.9415 | 6
|  | Skewness |  |  | 31.528 |  | 0.082561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97031 | 894 | 0.86105 | 0 | 1 | 0 | 0.97031 | 895 | 0.86105 | 0 | 0.97031 | 895 | 1 | 0 | 1 | 0 | 0.99715 | 999 | 0.082561 | 0 | 0 | 0 | 0.99715 | 999 | 1 | 0 | 1 | 0 | 1 | 0 | 46.9543 | 12 | 0.96667 | 552 | 30222.2335 | 8
|  | Kurtosis |  |  | 996.006
|  | Coeff. of Variability |  |  | 31.6228
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 1
|  | Mean Std. Error |  |  | 0.001
Forecast: A-B-D-E-F-H-K-L-M (cont'd) | [5 empty] | Cell: H19
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 0
|  |  | 30% |  | 0
|  |  | 40% |  | 0
|  |  | 50% |  | 0
|  |  | 60% |  | 0
|  |  | 70% |  | 0
|  |  | 80% |  | 0
|  |  | 90% |  | 0
|  |  | 100% |  | 1
End of Forecast
Forecast: A-C-E-F-H-K-L-M | [5 empty] | Cell: H20
Summary:
Display Range is from 0.0000 to 0.0000
Entire Range is from 0.0000 to 0.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0000
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0
|  | Median |  |  | 0
|  | Mode |  |  | 0
|  | Standard Deviation |  |  | 0
|  | Variance |  |  | 0
|  | Skewness |  |  | 0
|  | Kurtosis |  |  | +Infinity
|  | Coeff. of Variability |  |  | +Infinity
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 0
|  | Range Width |  |  | 0
|  | Mean Std. Error |  |  | 0
Forecast: A-C-E-F-H-K-L-M (cont'd) | [5 empty] | Cell: H20
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 0
|  |  | 30% |  | 0
|  |  | 40% |  | 0
|  |  | 50% |  | 0
|  |  | 60% |  | 0
|  |  | 70% |  | 0
|  |  | 80% |  | 0
|  |  | 90% |  | 0
|  |  | 100% |  | 0
End of Forecast
Forecast: A-B-D-E-F-I-K-L-M | [5 empty] | Cell: H21
Summary:
Display Range is from 0.0000 to 0.0000
Entire Range is from 0.0000 to 0.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0000
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0
|  | Median |  |  | 0
|  | Mode |  |  | 0
|  | Standard Deviation |  |  | 0
|  | Variance |  |  | 0
|  | Skewness |  |  | 0
|  | Kurtosis |  |  | +Infinity
|  | Coeff. of Variability |  |  | +Infinity
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 0
|  | Range Width |  |  | 0
|  | Mean Std. Error |  |  | 0
Forecast: A-B-D-E-F-I-K-L-M (cont'd) | [5 empty] | Cell: H21
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 0
|  |  | 30% |  | 0
|  |  | 40% |  | 0
|  |  | 50% |  | 0
|  |  | 60% |  | 0
|  |  | 70% |  | 0
|  |  | 80% |  | 0
|  |  | 90% |  | 0
|  |  | 100% |  | 0
End of Forecast
Forecast: A-C-E-F-I-K-L-M | [5 empty] | Cell: H22
Summary:
Display Range is from 0.0000 to 0.0000
Entire Range is from 0.0000 to 0.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0000
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0
|  | Median |  |  | 0
|  | Mode |  |  | 0
|  | Standard Deviation |  |  | 0
|  | Variance |  |  | 0
|  | Skewness |  |  | 0
|  | Kurtosis |  |  | +Infinity
|  | Coeff. of Variability |  |  | +Infinity
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 0
|  | Range Width |  |  | 0
|  | Mean Std. Error |  |  | 0
Forecast: A-C-E-F-I-K-L-M (cont'd) | [5 empty] | Cell: H22
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 0
|  |  | 30% |  | 0
|  |  | 40% |  | 0
|  |  | 50% |  | 0
|  |  | 60% |  | 0
|  |  | 70% |  | 0
|  |  | 80% |  | 0
|  |  | 90% |  | 0
|  |  | 100% |  | 0
End of Forecast
Forecast: A-B-D-E-F-G-J-K-L-M | [5 empty] | Cell: H23
Summary:
Display Range is from 0.1093 to 1.0000
Entire Range is from 0.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0097
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0.894
|  | Median |  |  | 1
|  | Mode |  |  | 1
|  | Standard Deviation |  |  | 0.30799
|  | Variance |  |  | 0.094859
|  | Skewness |  |  | -2.556
|  | Kurtosis |  |  | 7.5374
|  | Coeff. of Variability |  |  | 0.34451
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 1
|  | Mean Std. Error |  |  | 0.0097396
Forecast: A-B-D-E-F-G-J-K-L-M (cont'd) | [5 empty] | Cell: H23
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 1
|  |  | 30% |  | 1
|  |  | 40% |  | 1
|  |  | 50% |  | 1
|  |  | 60% |  | 1
|  |  | 70% |  | 1
|  |  | 80% |  | 1
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: A-C-E-F-G-J-K-L-M | [5 empty] | Cell: H24
Summary:
Display Range is from 0.0000 to 0.8907
Entire Range is from 0.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0097
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0.105
|  | Median |  |  | 0
|  | Mode |  |  | 0
|  | Standard Deviation |  |  | 0.30671
|  | Variance |  |  | 0.094069
|  | Skewness |  |  | 2.5732
|  | Kurtosis |  |  | 7.6259
|  | Coeff. of Variability |  |  | 2.921
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 1
|  | Mean Std. Error |  |  | 0.0096989
Forecast: A-C-E-F-G-J-K-L-M (cont'd) | [5 empty] | Cell: H24
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 0
|  |  | 30% |  | 0
|  |  | 40% |  | 0
|  |  | 50% |  | 0
|  |  | 60% |  | 0
|  |  | 70% |  | 0
|  |  | 80% |  | 0
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: A | [5 empty] | Cell: N2
Summary:
Display Range is from 1.0000 to 1.0000
Entire Range is from 1.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0000
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 1
|  | Median |  |  | 1
|  | Mode |  |  | 1
|  | Standard Deviation |  |  | 0
|  | Variance |  |  | 0
|  | Skewness |  |  | 0
|  | Kurtosis |  |  | +Infinity
|  | Coeff. of Variability |  |  | 0
|  | Range Minimum |  |  | 1
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 0
|  | Mean Std. Error |  |  | 0
Forecast: A (cont'd) | [5 empty] | Cell: N2
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 1
|  |  | 10% |  | 1
|  |  | 20% |  | 1
|  |  | 30% |  | 1
|  |  | 40% |  | 1
|  |  | 50% |  | 1
|  |  | 60% |  | 1
|  |  | 70% |  | 1
|  |  | 80% |  | 1
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: B | [5 empty] | Cell: N3
Summary:
Display Range is from 0.1093 to 1.0000
Entire Range is from 0.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0097
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0.895
|  | Median |  |  | 1
|  | Mode |  |  | 1
|  | Standard Deviation |  |  | 0.30671
|  | Variance |  |  | 0.094069
|  | Skewness |  |  | -2.5732
|  | Kurtosis |  |  | 7.6259
|  | Coeff. of Variability |  |  | 0.34269
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 1
|  | Mean Std. Error |  |  | 0.0096989
Forecast: B (cont'd) | [5 empty] | Cell: N3
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 1
|  |  | 30% |  | 1
|  |  | 40% |  | 1
|  |  | 50% |  | 1
|  |  | 60% |  | 1
|  |  | 70% |  | 1
|  |  | 80% |  | 1
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: C | [5 empty] | Cell: N4
Summary:
Display Range is from 0.0000 to 0.8907
Entire Range is from 0.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0097
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0.105
|  | Median |  |  | 0
|  | Mode |  |  | 0
|  | Standard Deviation |  |  | 0.30671
|  | Variance |  |  | 0.094069
|  | Skewness |  |  | 2.5732
|  | Kurtosis |  |  | 7.6259
|  | Coeff. of Variability |  |  | 2.921
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 1
|  | Mean Std. Error |  |  | 0.0096989
Forecast: C (cont'd) | [5 empty] | Cell: N4
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 0
|  |  | 30% |  | 0
|  |  | 40% |  | 0
|  |  | 50% |  | 0
|  |  | 60% |  | 0
|  |  | 70% |  | 0
|  |  | 80% |  | 0
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: D | [5 empty] | Cell: N5
Summary:
Display Range is from 0.1093 to 1.0000
Entire Range is from 0.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0097
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0.895
|  | Median |  |  | 1
|  | Mode |  |  | 1
|  | Standard Deviation |  |  | 0.30671
|  | Variance |  |  | 0.094069
|  | Skewness |  |  | -2.5732
|  | Kurtosis |  |  | 7.6259
|  | Coeff. of Variability |  |  | 0.34269
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 1
|  | Mean Std. Error |  |  | 0.0096989
Forecast: D (cont'd) | [5 empty] | Cell: N5
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 1
|  |  | 30% |  | 1
|  |  | 40% |  | 1
|  |  | 50% |  | 1
|  |  | 60% |  | 1
|  |  | 70% |  | 1
|  |  | 80% |  | 1
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: E | [5 empty] | Cell: N6
Summary:
Display Range is from 1.0000 to 1.0000
Entire Range is from 1.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0000
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 1
|  | Median |  |  | 1
|  | Mode |  |  | 1
|  | Standard Deviation |  |  | 0
|  | Variance |  |  | 0
|  | Skewness |  |  | 0
|  | Kurtosis |  |  | +Infinity
|  | Coeff. of Variability |  |  | 0
|  | Range Minimum |  |  | 1
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 0
|  | Mean Std. Error |  |  | 0
Forecast: E (cont'd) | [5 empty] | Cell: N6
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 1
|  |  | 10% |  | 1
|  |  | 20% |  | 1
|  |  | 30% |  | 1
|  |  | 40% |  | 1
|  |  | 50% |  | 1
|  |  | 60% |  | 1
|  |  | 70% |  | 1
|  |  | 80% |  | 1
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: F | [5 empty] | Cell: N7
Summary:
Display Range is from 1.0000 to 1.0000
Entire Range is from 1.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0000
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 1
|  | Median |  |  | 1
|  | Mode |  |  | 1
|  | Standard Deviation |  |  | 0
|  | Variance |  |  | 0
|  | Skewness |  |  | 0
|  | Kurtosis |  |  | +Infinity
|  | Coeff. of Variability |  |  | 0
|  | Range Minimum |  |  | 1
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 0
|  | Mean Std. Error |  |  | 0
Forecast: F (cont'd) | [5 empty] | Cell: N7
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 1
|  |  | 10% |  | 1
|  |  | 20% |  | 1
|  |  | 30% |  | 1
|  |  | 40% |  | 1
|  |  | 50% |  | 1
|  |  | 60% |  | 1
|  |  | 70% |  | 1
|  |  | 80% |  | 1
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: G | [5 empty] | Cell: N8
Summary:
Display Range is from 0.9146 to 1.0000
Entire Range is from 0.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0010
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0.999
|  | Median |  |  | 1
|  | Mode |  |  | 1
|  | Standard Deviation |  |  | 0.031623
|  | Variance |  |  | 0.001
|  | Skewness |  |  | -31.528
|  | Kurtosis |  |  | 996.006
|  | Coeff. of Variability |  |  | 0.031654
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 1
|  | Mean Std. Error |  |  | 0.001
Forecast: G (cont'd) | [5 empty] | Cell: N8
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 1
|  |  | 20% |  | 1
|  |  | 30% |  | 1
|  |  | 40% |  | 1
|  |  | 50% |  | 1
|  |  | 60% |  | 1
|  |  | 70% |  | 1
|  |  | 80% |  | 1
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: H | [5 empty] | Cell: N9
Summary:
Display Range is from 0.0000 to 0.0854
Entire Range is from 0.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0010
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0.001
|  | Median |  |  | 0
|  | Mode |  |  | 0
|  | Standard Deviation |  |  | 0.031623
|  | Variance |  |  | 0.001
|  | Skewness |  |  | 31.528
|  | Kurtosis |  |  | 996.006
|  | Coeff. of Variability |  |  | 31.6228
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 1
|  | Mean Std. Error |  |  | 0.001
Forecast: H (cont'd) | [5 empty] | Cell: N9
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 0
|  |  | 30% |  | 0
|  |  | 40% |  | 0
|  |  | 50% |  | 0
|  |  | 60% |  | 0
|  |  | 70% |  | 0
|  |  | 80% |  | 0
|  |  | 90% |  | 0
|  |  | 100% |  | 1
End of Forecast
Forecast: I | [5 empty] | Cell: N10
Summary:
Display Range is from 0.0000 to 0.0000
Entire Range is from 0.0000 to 0.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0000
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0
|  | Median |  |  | 0
|  | Mode |  |  | 0
|  | Standard Deviation |  |  | 0
|  | Variance |  |  | 0
|  | Skewness |  |  | 0
|  | Kurtosis |  |  | +Infinity
|  | Coeff. of Variability |  |  | +Infinity
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 0
|  | Range Width |  |  | 0
|  | Mean Std. Error |  |  | 0
Forecast: I (cont'd) | [5 empty] | Cell: N10
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 0
|  |  | 30% |  | 0
|  |  | 40% |  | 0
|  |  | 50% |  | 0
|  |  | 60% |  | 0
|  |  | 70% |  | 0
|  |  | 80% |  | 0
|  |  | 90% |  | 0
|  |  | 100% |  | 0
End of Forecast
Forecast: J | [5 empty] | Cell: N12
Summary:
Display Range is from 0.9146 to 1.0000
Entire Range is from 0.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0010
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0.999
|  | Median |  |  | 1
|  | Mode |  |  | 1
|  | Standard Deviation |  |  | 0.031623
|  | Variance |  |  | 0.001
|  | Skewness |  |  | -31.528
|  | Kurtosis |  |  | 996.006
|  | Coeff. of Variability |  |  | 0.031654
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 1
|  | Mean Std. Error |  |  | 0.001
Forecast: J (cont'd) | [5 empty] | Cell: N12
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 1
|  |  | 20% |  | 1
|  |  | 30% |  | 1
|  |  | 40% |  | 1
|  |  | 50% |  | 1
|  |  | 60% |  | 1
|  |  | 70% |  | 1
|  |  | 80% |  | 1
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: K | [5 empty] | Cell: N13
Summary:
Display Range is from 1.0000 to 1.0000
Entire Range is from 1.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0000
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 1
|  | Median |  |  | 1
|  | Mode |  |  | 1
|  | Standard Deviation |  |  | 0
|  | Variance |  |  | 0
|  | Skewness |  |  | 0
|  | Kurtosis |  |  | +Infinity
|  | Coeff. of Variability |  |  | 0
|  | Range Minimum |  |  | 1
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 0
|  | Mean Std. Error |  |  | 0
Forecast: K (cont'd) | [5 empty] | Cell: N13
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 1
|  |  | 10% |  | 1
|  |  | 20% |  | 1
|  |  | 30% |  | 1
|  |  | 40% |  | 1
|  |  | 50% |  | 1
|  |  | 60% |  | 1
|  |  | 70% |  | 1
|  |  | 80% |  | 1
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: L | [5 empty] | Cell: N14
Summary:
Display Range is from 1.0000 to 1.0000
Entire Range is from 1.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0000
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 1
|  | Median |  |  | 1
|  | Mode |  |  | 1
|  | Standard Deviation |  |  | 0
|  | Variance |  |  | 0
|  | Skewness |  |  | 0
|  | Kurtosis |  |  | +Infinity
|  | Coeff. of Variability |  |  | 0
|  | Range Minimum |  |  | 1
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 0
|  | Mean Std. Error |  |  | 0
Forecast: L (cont'd) | [5 empty] | Cell: N14
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 1
|  |  | 10% |  | 1
|  |  | 20% |  | 1
|  |  | 30% |  | 1
|  |  | 40% |  | 1
|  |  | 50% |  | 1
|  |  | 60% |  | 1
|  |  | 70% |  | 1
|  |  | 80% |  | 1
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: M | [5 empty] | Cell: N15
Summary:
Display Range is from 1.0000 to 1.0000
Entire Range is from 1.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0000
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 1
|  | Median |  |  | 1
|  | Mode |  |  | 1
|  | Standard Deviation |  |  | 0
|  | Variance |  |  | 0
|  | Skewness |  |  | 0
|  | Kurtosis |  |  | +Infinity
|  | Coeff. of Variability |  |  | 0
|  | Range Minimum |  |  | 1
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 0
|  | Mean Std. Error |  |  | 0
Forecast: M (cont'd) | [5 empty] | Cell: N15
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 1
|  |  | 10% |  | 1
|  |  | 20% |  | 1
|  |  | 30% |  | 1
|  |  | 40% |  | 1
|  |  | 50% |  | 1
|  |  | 60% |  | 1
|  |  | 70% |  | 1
|  |  | 80% |  | 1
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: Project Time | [5 empty] | Cell: B30
Summary:
Display Range is from 38.3664 to 47.2504
Entire Range is from 37.9599 to 48.5571
After 1,000 Trials, the Std. Error of the Mean is 0.0546
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 42.853
|  | Median |  |  | 42.7545
|  | Mode |  |  | ---
|  | Standard Deviation |  |  | 1.7251
|  | Variance |  |  | 2.976
|  | Skewness |  |  | 0.11454
|  | Kurtosis |  |  | 2.9498
|  | Coeff. of Variability |  |  | 0.040257
|  | Range Minimum |  |  | 37.9599
|  | Range Maximum |  |  | 48.5571
|  | Range Width |  |  | 10.5972
|  | Mean Std. Error |  |  | 0.054553
Forecast: Project Time (cont'd) | [5 empty] | Cell: B30
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 37.9599
|  |  | 10% |  | 40.7655
|  |  | 20% |  | 41.4373
|  |  | 30% |  | 41.911
|  |  | 40% |  | 42.3508
|  |  | 50% |  | 42.7545
|  |  | 60% |  | 43.1784
|  |  | 70% |  | 43.7463
|  |  | 80% |  | 44.3217
|  |  | 90% |  | 45.1695
|  |  | 100% |  | 48.5571
End of Forecast
Forecast: <= 43? | [5 empty] | Cell: C30
Summary:
Display Range is from 0.0000 to 1.0000
Entire Range is from 0.0000 to 1.0000
After 1,000 Trials, the Std. Error of the Mean is 0.0157
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 0.552
|  | Median |  |  | 1
|  | Mode |  |  | 1
|  | Standard Deviation |  |  | 0.49754
|  | Variance |  |  | 0.24754
|  | Skewness |  |  | -0.20882
|  | Kurtosis |  |  | 1.0417
|  | Coeff. of Variability |  |  | 0.90134
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 1
|  | Range Width |  |  | 1
|  | Mean Std. Error |  |  | 0.015734
Forecast: <= 43? (cont'd) | [5 empty] | Cell: C30
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 0
|  |  | 30% |  | 0
|  |  | 40% |  | 0
|  |  | 50% |  | 1
|  |  | 60% |  | 1
|  |  | 70% |  | 1
|  |  | 80% |  | 1
|  |  | 90% |  | 1
|  |  | 100% |  | 1
End of Forecast
Forecast: Penalty | [5 empty] | Cell: D30
Summary:
Display Range is from $0 to $31,264
Entire Range is from $0 to $55,571
After 1,000 Trials, the Std. Error of the Mean is $312
| Statistics: |  |  |  | Value
|  | Trials |  |  | 1000
|  | Mean |  |  | 6192.9644
|  | Median |  |  | 0
|  | Mode |  |  | 0
|  | Standard Deviation |  |  | 9863.1366
|  | Variance |  |  | 97281463.8453
|  | Skewness |  |  | 1.762
|  | Kurtosis |  |  | 5.7133
|  | Coeff. of Variability |  |  | 1.5926
|  | Range Minimum |  |  | 0
|  | Range Maximum |  |  | 55571.2716
|  | Range Width |  |  | 55571.2716
|  | Mean Std. Error |  |  | 311.8998
Forecast: Penalty (cont'd) | [5 empty] | Cell: D30
Percentiles:
|  |  | Percentile |  | Value
|  |  | 0% |  | 0
|  |  | 10% |  | 0
|  |  | 20% |  | 0
|  |  | 30% |  | 0
|  |  | 40% |  | 0
|  |  | 50% |  | 0
|  |  | 60% |  | 1783.9454
|  |  | 70% |  | 7463.0543
|  |  | 80% |  | 13217.4663
|  |  | 90% |  | 21694.7976
|  |  | 100% |  | 55571.2716
End of Forecast

## Textbook Model
Activity | Description | Optimistic | Pessimistic | Most-likely | Predecessors | Start Node | End Node | Mean | StDev
A | Survey Site | 2 | 4 | 3 | None | 0 | 1 | 3 | 0.33333
B | Excavation | 9 | 15 | 12 | A | 1 | 2 | 12 | 1
C | Prepare Drawings | 4 | 18 | 9 | None | 0 | 3 | 9.6667 | 2.3333
D | Soil Study | 1 | 1 | 1 | B | 2 | 3 | 1 | 0
E | Prelim. Report | 1 | 3 | 2 | C, D | 3 | 4 | 2 | 0.33333
F | Approve Plans | 1 | 1 | 1 | E | 4 | 5 | 1 | 0
G | Concrete Forms | 5 | 9 | 6 | F | 5 | 7 | 6.3333 | 0.66667
H | Procure Steel | 2 | 10 | 5 | F | 5 | 6 | 5.3333 | 1.3333
I | Order Cement | 1 | 1 | 1 | F | 5 | 8 | 1 | 0
Dummy |  | 0 | 0 | 0 | H | 6 | 8 | 0 | 0
J | Deliver Gravel | 2 | 5 | 3 | G | 7 | 8 | 3.1667 | 0.5
K | Pour Concrete | 8 | 14 | 10 | H, I, J | 8 | 9 | 10.3333 | 1
L | Cure Concrete | 2 | 2 | 2 | K | 9 | 10 | 2 | 0
M | Strength Test | 2 | 2 | 2 | L | 10 | 11 | 2 | 0
|  |  | Path |  |  | Sum of Means | Sum of Variances
|  |  | A-B-D-E-F-H-K-L-M |  |  | 38.6667
|  |  | A-C-E-F-H-K-L-M |  |  | 35.3333
|  |  | A-B-D-E-F-I-K-L-M |  |  | 34.3333
|  |  | A-C-E-F-I-K-L-M |  |  | 31
|  |  | A-B-D-E-F-G-J-K-L-M |  |  | 42.8333 | 2.9167 | 1.7078
|  |  | A-C-E-F-G-J-K-L-M |  |  | 39.5
[7 empty] | 90% completion time | 46.5712
[7 empty] | Prob(X < 43) | 0.53887
Note on I23: =SQRT(H23)
Note on I27: =NORMDIST(43,G23,I23,1)

## PERT Calcs
Activity | Description | Optimistic | Pessimistic | Most-likely | Predecessors | Start Node | End Node | Mean | StDev | Alpha | Beta | Scale
A | Survey Site | 2 | 4 | 3 | None | 0 | 1 | 3 | 0.33333 | 4 | 4 | 2
B | Excavation | 9 | 15 | 12 | A | 1 | 2 | 12 | 1 | 4 | 4 | 6
C | Prepare Drawings | 4 | 18 | 9 | None | 0 | 3 | 9.6667 | 2.3333 | 3.1059 | 4.5675 | 14
D | Soil Study | 1 | 1 | 1 | B | 2 | 3 | 1 | 0 |  |  | 0
E | Prelim. Report | 1 | 3 | 2 | C, D | 3 | 4 | 2 | 0.33333 | 4 | 4 | 2
F | Approve Plans | 1 | 1 | 1 | E | 4 | 5 | 1 | 0 |  |  | 0
G | Concrete Forms | 5 | 9 | 6 | F | 5 | 7 | 6.3333 | 0.66667 | 2.3333 | 4.6667 | 4
H | Procure Steel | 2 | 10 | 5 | F | 5 | 6 | 5.3333 | 1.3333 | 3.2292 | 4.5208 | 8
I | Order Cement | 1 | 1 | 1 | F | 5 | 8 | 1 | 0 |  |  | 0
Dummy |  | 0 | 0 | 0 | H | 6 | 8 | 0 | 0 |  |  | 0
J | Deliver Gravel | 2 | 5 | 3 | G | 7 | 8 | 3.1667 | 0.5 | 2.9383 | 4.6173 | 3
K | Pour Concrete | 8 | 14 | 10 | H, I, J | 8 | 9 | 10.3333 | 1 | 2.9383 | 4.6173 | 6
L | Cure Concrete | 2 | 2 | 2 | K | 9 | 10 | 2 | 0 |  |  | 0
M | Strength Test | 2 | 2 | 2 | L | 10 | 11 | 2 | 0 |  |  | 0
Note on K3: =((I3-C3)/(D3-C3))*((((I3-C3)*(D3-I3))/(J3^2))-1)
Note on L4: =((D4-I4)/(I4-C4))*K4
Note on M5: =D5-C5

## HOM CPM
Critical Path Method Calculations Results.
Activity | Early | Early | Late | Late
Name | Start | Finish | Start | Finish | Slack | Description
======== | ======== | ======== | ======== | ======== | ======== | ================
A | 0 | 3 | 0 | 3 | 0
B | 3 | 15 | 3 | 15 | 0
C | 0 | 9 | 7 | 16 | 7
D | 15 | 16 | 15 | 16 | 0
E | 16 | 18 | 16 | 18 | 0
F | 18 | 19 | 18 | 19 | 0
G | 19 | 25 | 19 | 25 | 0
H | 19 | 24 | 23 | 28 | 4
I | 19 | 20 | 27 | 28 | 8
J | 25 | 28 | 25 | 28 | 0
K | 28 | 38 | 28 | 38 | 0
L | 38 | 40 | 38 | 40 | 0
M | 40 | 42 | 40 | 42 | 0
Expected Completion Time : | 42
Critical Path:
A | B | D | E | F | G | J | K | L | M

## HOM no sim
PERT Calculations Results.
Activity | Early | Early | Late | Late
Name | Start | Finish | Start | Finish | Slack | Description
======== | ======== | ======== | ======== | ======== | ======== | ================
A | 0 | 3 | 0 | 3 | 0
B | 3 | 15 | 3 | 15 | 0
C | 0 | 9.6667 | 6.3333 | 16 | 6.3333
D | 15 | 16 | 15 | 16 | 0
E | 16 | 18 | 16 | 18 | 0
F | 18 | 19 | 18 | 19 | 0
G | 19 | 25.3333 | 19 | 25.3333 | 0
H | 19 | 24.3333 | 23.1667 | 28.5 | 4.1667
I | 19 | 20 | 27.5 | 28.5 | 8.5
J | 25.3333 | 28.5 | 25.3333 | 28.5 | 0
K | 28.5 | 38.8333 | 28.5 | 38.8333 | 0
L | 38.8333 | 40.8333 | 38.8333 | 40.8333 | 0
M | 40.8333 | 42.8333 | 40.8333 | 42.8333 | 0
Expected Completion Time : | 42.8333
Standard Deviation on CP : | 1.7078
Critical Path:
A | B | D | E | F | G | J | K | L | M
Probability of Project Completion.
Time to | Probablity
Complete | of
Project | Completion
======== | ======== |  | Midpoint | Prob | Penalty
37.7099 | 0.001354 |  | 18.8549 | 0.001354 | 0
38.0514 | 0.002562 |  | 37.8807 | 0.001208 | 0
38.393 | 0.00467 |  | 38.2222 | 0.002108 | 0
38.7346 | 0.008208 |  | 38.5638 | 0.003538 | 0
39.0761 | 0.013914 |  | 38.9053 | 0.005706 | 0
39.4177 | 0.022758 |  | 39.2469 | 0.008844 | 0
39.7592 | 0.035934 |  | 39.5885 | 0.013176 | 0
40.1008 | 0.054797 |  | 39.93 | 0.018863 | 0
40.4424 | 0.080748 |  | 40.2716 | 0.025951 | 0
40.7839 | 0.11506 |  | 40.6131 | 0.034311 | 0
41.1255 | 0.15865 |  | 40.9547 | 0.04359 | 0
41.4671 | 0.21186 |  | 41.2963 | 0.053209 | 0
41.8086 | 0.27426 |  | 41.6379 | 0.062406 | 0
42.1502 | 0.34459 |  | 41.9794 | 0.070323 | 0
42.4918 | 0.42073 |  | 42.321 | 0.076147 | 0
42.8333 | 0.5 |  | 42.6626 | 0.079266 | 0
43.1749 | 0.57927 |  | 43.0041 | 0.079266 | 41
43.5165 | 0.65541 |  | 43.3457 | 0.076147 | 3457
43.858 | 0.72574 |  | 43.6872 | 0.070323 | 6872.5
44.1996 | 0.78814 |  | 44.0288 | 0.062406 | 10288
44.5412 | 0.84135 |  | 44.3704 | 0.053209 | 13704
44.8827 | 0.88494 |  | 44.712 | 0.04359 | 17119.5
45.2243 | 0.91925 |  | 45.0535 | 0.03431 | 20535
45.5659 | 0.9452 |  | 45.3951 | 0.025952 | 23951
45.9074 | 0.96407 |  | 45.7366 | 0.018863 | 27366.5
46.249 | 0.97724 |  | 46.0782 | 0.013175 | 30782
46.5905 | 0.98609 |  | 46.4198 | 0.008845 | 34197.5
46.9321 | 0.99179 |  | 46.7613 | 0.005706 | 37613
47.2737 | 0.99533 |  | 47.1029 | 0.003538 | 41029
47.6152 | 0.99744 |  | 47.4445 | 0.002108 | 44444.5
47.9568 | 0.99865 |  | 47.786 | 0.001207 | 47860
| 1 |  | 66.8117 | 0.001355 | 238117
|  |  |  | 1 |  | 6251.4941

## Criticality Summary
Activities |  |  |  |  | Paths | Crystal Ball | Textbook | HOM (no simulation) | HOM (simulation)
| Crystal Ball | Textbook | HOM (no simulation) | HOM (simulation) | A-B-D-E-F-H-K-L-M | 0.001 | 0 | 0
A | 1 | 1 | 1 | 0.99 | A-C-E-F-H-K-L-M | 0 | 0 | 0 |  | 0.002
B | 0.895 | 1 | 1 | 0.99 | A-B-D-E-F-I-K-L-M | 0 | 0 | 0 | 0
C | 0.105 | 0 | 0 | 0.01 | A-C-E-F-I-K-L-M | 0 | 0 | 0 | 0
D | 0.895 | 1 | 1 | 0.99 | A-B-D-E-F-G-J-K-L-M | 0.894 | 1 | 1 |  | 0.998
E | 1 | 1 | 1 | 1 | A-C-E-F-G-J-K-L-M | 0.105 | 0 | 0
F | 1 | 1 | 1 | 1
G | 0.999 | 1 | 1 | 0.998
H | 0.001 | 0 | 0 | 0.002
I | 0 | 0 | 0 | 0
J | 0.999 | 1 | 1 | 0.998 |  | ABD | C
K | 1 | 1 | 1 | 1 | GJ | ? |  | 0.998
L | 1 | 1 | 1 | 1 | H |  |  | 0.002
M | 1 | 1 | 1 | 1 |  | 99% | 0.01

## HOM sim
PERT Simulation (Criticality) Calculations Results.
Activity | Criticality
Name | Indices | Description
======== | ======== | ================
A | 99%
B | 99%
C | 1%
D | 99%
E | 100%
F | 100%
G | 99.8%
H | 0.2%
I | 0%
J | 99.8%
K | 100%
L | 100%
M | 100%
Project completion time:
| Minimum : | 38.3251
| Maximum : | 48.8158
| Mean : | 42.893
| Standard Deviation : | 1.7468
Completion frequency distribution (1000 runs performed):
Interval | Interval | Frequency
Start | End | (%) | (Counts) | Cumulative | Prob | Midpoint | Penalty
======== | ======== | ======== | ========
38.33 | 39.37 | 1.6 | 16 | 1.6 | 0.016016 | 38.85 | 0
39.37 | 40.42 | 6.3 | 63 | 7.9 | 0.063063 | 39.895 | 0
40.42 | 41.47 | 12.9 | 129 | 20.8 | 0.12913 | 40.945 | 0
41.47 | 42.52 | 21.1 | 211 | 41.9 | 0.21121 | 41.995 | 0
42.52 | 43.57 | 24.5 | 245 | 66.4 | 0.24525 | 43.045 | 450
43.57 | 44.62 | 17.1 | 171 | 83.5 | 0.17117 | 44.095 | 10950
44.62 | 45.67 | 10.7 | 107 | 94.2 | 0.10711 | 45.145 | 21450
45.67 | 46.72 | 4.2 | 42 | 98.4 | 0.042042 | 46.195 | 31950
46.72 | 47.77 | 1.3 | 13 | 99.7 | 0.013013 | 47.245 | 42450
47.77 | 48.82 | 0.2 | 2 | 99.9 | 0.002002 | 48.295 | 52950
|  |  | 999 |  |  |  | 6283.7838

## DATA
Statistics | A-B-D-E-F-H-K-L-M | A-C-E-F-H-K-L-M | A-B-D-E-F-I-K-L-M | A-C-E-F-I-K-L-M | A-B-D-E-F-G-J-K-L-M | A-C-E-F-G-J-K-L-M | A | B | C | D | E | F | G | H | I | J | K | L | M | Project Time | <= 43? | Penalty
Trials | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
Mean | 0.001 | 0 | 0 | 0 | 0.894 | 0.105 | 1 | 0.895 | 0.105 | 0.895 | 1 | 1 | 0.999 | 0.001 | 0 | 0.999 | 1 | 1 | 1 | 42.853 | 0.552 | 6192.9644
Median | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 42.7545 | 1 | 0
Mode | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | --- | 1 | 0
Standard Deviation | 0.031623 | 0 | 0 | 0 | 0.30799 | 0.30671 | 0 | 0.30671 | 0.30671 | 0.30671 | 0 | 0 | 0.031623 | 0.031623 | 0 | 0.031623 | 0 | 0 | 0 | 1.7251 | 0.49754 | 9863.1366
Variance | 0.001 | 0 | 0 | 0 | 0.094859 | 0.094069 | 0 | 0.094069 | 0.094069 | 0.094069 | 0 | 0 | 0.001 | 0.001 | 0 | 0.001 | 0 | 0 | 0 | 2.976 | 0.24754 | 97281463.8453
Skewness | 31.528 | 0 | 0 | 0 | -2.556 | 2.5732 | 0 | -2.5732 | 2.5732 | -2.5732 | 0 | 0 | -31.528 | 31.528 | 0 | -31.528 | 0 | 0 | 0 | 0.11454 | -0.20882 | 1.762
Kurtosis | 996.006 | +Infinity | +Infinity | +Infinity | 7.5374 | 7.6259 | +Infinity | 7.6259 | 7.6259 | 7.6259 | +Infinity | +Infinity | 996.006 | 996.006 | +Infinity | 996.006 | +Infinity | +Infinity | +Infinity | 2.9498 | 1.0417 | 5.7133
Coeff. of Variability | 31.6228 | +Infinity | +Infinity | +Infinity | 0.34451 | 2.921 | 0 | 0.34269 | 2.921 | 0.34269 | 0 | 0 | 0.031654 | 31.6228 | +Infinity | 0.031654 | 0 | 0 | 0 | 0.040257 | 0.90134 | 1.5926
Range Minimum | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 37.9599 | 0 | 0
Range Maximum | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 48.5571 | 1 | 55571.2716
Range Width | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 10.5972 | 1 | 55571.2716
Mean Std. Error | 0.001 | 0 | 0 | 0 | 0.0097396 | 0.0096989 | 0 | 0.0096989 | 0.0096989 | 0.0096989 | 0 | 0 | 0.001 | 0.001 | 0 | 0.001 | 0 | 0 | 0 | 0.054553 | 0.015734 | 311.8998
| A-B-D-E-F-H-K-L-M | 1000 | 0.001 |  |  |  | J: A; K: 1000; L: 1 | Activity | Estimated Probability of being Critical
| A-C-E-F-H-K-L-M | 1000 | 0 |  |  |  | J: B; K: 1000; L: 0.895 | A | 1
| A-B-D-E-F-I-K-L-M | 1000 | 0 |  |  |  | J: C; K: 1000; L: 0.105 | E | 1
| A-C-E-F-I-K-L-M | 1000 | 0 |  |  |  | J: D; K: 1000; L: 0.895 | F | 1
| A-B-D-E-F-G-J-K-L-M | 1000 | 0.894 |  |  |  | J: E; K: 1000; L: 1 | K | 1
| A-C-E-F-G-J-K-L-M | 1000 | 0.105 |  |  |  | J: F; K: 1000; L: 1 | L | 1
[7 empty] | J: G; K: 1000; L: 0.999 | M | 1
|  |  | 1 |  |  |  | J: H; K: 1000; L: 0.001 | G | 0.999
[7 empty] | J: I; K: 1000; L: 0 | J | 0.999
[7 empty] | J: J; K: 1000; L: 0.999 | B | 0.895
[7 empty] | J: K; K: 1000; L: 1 | D | 0.895
[7 empty] | J: L; K: 1000; L: 1 | C | 0.105
[7 empty] | J: M; K: 1000; L: 1 | H | 0.001
[20 empty] | I | 0