## Slide 1: The Beach House … …gone bad!
Dahlia Kang
Vishal Rana
Eric Updegraff
Jon Howell
Decision Models – Spring 2003

## Slide 2: Problem Definition
Joint project to build a house
Option such as flooring, home theater, cabinets, etc need to be selected
Each person has different values (utility) for each item

## Slide 3: Need to choose options

## Slide 4
=SUMPRODUCT(J5:J33,Q5:Q33)+SUMPRODUCT(K5:K33,Q5:Q33)+SUMPRODUCT(L5:L33,Q5:Q33)+SUMPRODUCT(M5:M33,Q5:Q33)
=SUMPRODUCT(C5:F36,J5:M36)
Values
Utility
Best Selection
Notes: Each person weighted the importance of options 1 to 4
Solver Model evaluates weightings and selects best option
Maximized utility should make everyone happy!

## Slide 5
=SUMPRODUCT(J5:J33,Q5:Q33)+SUMPRODUCT(K5:K33,Q5:Q33)+SUMPRODUCT(L5:L33,Q5:Q33)+SUMPRODUCT(M5:M33,Q5:Q33)
=SUMPRODUCT(C5:F36,J5:M36)
Values
Notes: Each person weighted the importance of options 1 to 4
Solver Model evaluates weightings and selects best option
Maximized utility should make everyone happy!

## Slide 6: Capitalism at work
Still maximize utility
Stay within budget
Partners who contribute more, get more say in what options are selected

## Slide 7
Solver Optimized
Maximized Value
=SUMIF($J$14:$J$42,1,E$14:E$42)
=J3*J5
=MIN(J7:J8)
Notes: Options chosen based on preferences/utiliies
In addition factors contribution into weighting of maximum value

## Slide 8
Solver Optimized
Maximized Value
=SUMIF($J$14:$J$42,1,E$14:E$42)
=J3*J5
=MIN(J7:J8)
Notes: Options chosen based on preferences/utiliies
In addition factors contribution into weighting of maximum value

## Slide 9
Solver Optimized
Maximized Value
=SUMIF($J$14:$J$42,1,E$14:E$42)
=J3*J5
=MIN(J7:J8)
Notes: Options chosen based on preferences/utiliies
In addition factors contribution into weighting of maximum value

## Slide 10: Get it done! Time to party …
Optimizes choices
Now we know how long it will take
Changed situation requires better suited model!

## Slide 11: Network Flow
t1
t0 - Start
Fireplace
B - 3
L/B Floor
H - 10
H/K/B Tile
G - 8
Master Bath
F – 2.5
Refrigerator
E – 0.5
Appliances
D - 2
Cabinets
C - 9
Home Theater
A – 1.5
t1
t3
t4
t5
t6 - End

## Slide 12
=SUMIF(D14:G14,1,D14:G14)
=VLOOKUP(1,H14:I17,2, FALSE)
=R5
=SUMPRODUCT($L$5:$R$5,L9:R9)
=G2

## Slide 13
=SUMIF(D14:G14,1,D14:G14)
=VLOOKUP(1,H14:I17,2, FALSE)
=R5
=SUMPRODUCT($L$5:$R$5,L9:R9)
=G2

## Slide 14: We’ll never make the party in 15 days!
Money talks
Crash time shows it can be done

## Slide 15: 15 days – ready to party!
=SUMPRODUCT(X8:X15,Z8:Z15)
=W8-X8

## Slide 16: 15 days – ready to party!
=SUMPRODUCT(X8:X15,Z8:Z15)
=W8-X8

## Slide 17: Judge Wapner rules!