## Model 4
Activity |  | Description | Predecessors |  | Duration (Days) |  | Cost per Day to Reduce | Max. Poss. Red. (Days) | Cost of Crash
A |  | Home Theater |  | H |  | 1.5 | 500 | 0.5 | 2235 |  |  |  | 15 |  | <-- | Max. Completion Time
B |  | Fireplace Finish |  | --- |  | 3 | 600 | 1
C |  | Cabinets |  | G |  | 9 | 350 | 2 |  | t0 | t1 | t2 | t3 | t4 | t5 | t6
D |  | Appliances |  | E |  | 2 | 200 | 0.5 |  | 0 | 3.5 | 13.5 | 6.1 | 13.1 | 13.5 | 15
E |  | Refrigerator |  | C |  | 0.5 | 100 | 0.1 | [10 empty] | Improved Duration | Basic Duration | Crash Time | Max. Crash | Cost/Time
F |  | Master Bath |  | G |  | 2.5 | 800 | 1.5 |  | t0 | t1 | t2 | t3 | t4 | t5 | t6
G |  | H/K/B Tile |  | --- |  | 8 | 750 | 2 | A | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 1.5 | >= | 1.5 | 1.5 | 0 | 0.5 | 500
H |  | L/B Floor |  | B |  | 10 | 400 | 4 | B | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 3.5 | >= | 3 | 3 | 0 | 1 | 600
[9 empty] | C | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 7 | >= | 7 | 9 | 2 | 2 | 350
Option | # | Description | [5 empty] | Time | D | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 1.5 | >= | 1.5 | 2 | 0.5 | 0.5 | 200
[8 empty] | (Days) | E | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0.4 | >= | 0.4 | 0.5 | 0.1 | 0.1 | 100
|  |  | Eric | Dahlia | Vishal | Jon | Decision |  | F | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 8.9 | >= | 2.5 | 2.5 | 0 | 1.5 | 800
Home Theater | 1 | JBL Home Cinema Package | 0 | 1 | 0 | 0 | 1 | 1.5 | G | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 6.1 | >= | 6.1 | 8 | 1.9 | 2 | 750
| 2 | JBL Cinema Propack | 0 | 0 | 0 | 0 | 0 | 1 | H | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 10 | >= | 10 | 10 | 0 | 4 | 400
| 3 | Harmon Kardon Dolby | 0 | 0 | 0 | 0 | 0 | 1
| 4 | JBL Simply Cinema Package | 0 | 0 | 0 | 0 | 0 | 1
Fireplace Finish | 1 | Savannah Stain | 0 | 1 | 0 | 0 | 1 | 3
| 2 | Mount Vernon Stain | 0 | 0 | 0 | 0 | 0 | 3
| 3 | Ellicott Paint Grade | 0 | 0 | 0 | 0 | 0 | 2
| 4 | Yorktown Paint Grade | 0 | 0 | 0 | 0 | 0 | 2
Cabinets | 1 | Eastland Maple Arch | 0 | 1 | 0 | 0 | 1 | 9
| 2 | Oxbridge Square Panel | 0 | 0 | 0 | 0 | 0 | 7
| 3 | York Square Panel | 0 | 0 | 0 | 0 | 0 | 7
| 4 | Standard | 0 | 0 | 0 | 0 | 0 | 4
Appliances | 1 | Super | 0 | 1 | 0 | 0 | 1 | 2
| 2 | Premium | 0 | 0 | 0 | 0 | 0 | 1.5
| 3 | Plus | 0 | 0 | 0 | 0 | 0 | 1.5
Refrigerator | 1 | 26.6 cu ft | 0 | 1 | 0 | 0 | 1 | 0.5
| 2 | 21.8 cu ft | 0 | 0 | 0 | 0 | 0 | 0.5
| 3 | 17.9 cu ft | 0 | 0 | 0 | 0 | 0 | 0.5
Master Bath | 1 | Ascenti Gold Fixtures | 0 | 1 | 0 | 0 | 1 | 2.5
| 2 | Moen Brass Collection | 0 | 0 | 0 | 0 | 0 | 2.5
| 3 | Jacuzzi Whirlpool Spa | 0 | 0 | 0 | 0 | 0 | 3
| 4 | Standard Chrome Fixtures | 0 | 0 | 0 | 0 | 0 | 2.5
Hall, Kitchen and Bath Tile | 1 | Level 3 | 0 | 1 | 0 | 0 | 1 | 8
| 2 | Level 2 | 0 | 0 | 0 | 0 | 0 | 5
| 3 | Level 1 | 0 | 0 | 0 | 0 | 0 | 3
Living/Bed-room Flooring | 1 | Hardwood Deluxe | 0 | 1 | 0 | 0 | 1 | 10
| 2 | Premium Carpet | 0 | 0 | 0 | 0 | 0 | 6
| 3 | Vinyl | 0 | 0 | 0 | 0 | 0 | 4
| 4 | Dirt floor | 0 | 0 | 0 | 0 | 0 | 0
Note on K2: =SUMPRODUCT(X8:X15,Z8:Z15)
Note on U8: =W8-X8

## Sheet3
Category |  | Option | Cost | Time
Home Theater | 1 | JBL Home Cinema Package | 2610 | 1.5
| 2 | JBL Cinema Propack | 1885 | 1
| 3 | Harmon Kardon Dolby | 1210 | 1
| 4 | JBL Simply Cinema Package | 1089 | 1
Fireplace Finish | 1 | Savannah Stain | 1165 | 3
| 2 | Mount Vernon Stain | 825 | 3
| 3 | Ellicott Paint Grade | 600 | 2
| 4 | Yorktown Paint Grade | 490 | 2
Cabinets | 1 | Eastland Maple Arch | 5314 | 9
| 2 | Oxbridge Square Panel | 3400 | 7
| 3 | York Square Panel | 2205 | 7
| 4 | Standard | 455 | 4
Appliances | 1 | Super | 1820 | 2
| 2 | Premium | 749 | 1.5
| 3 | Plus | 415 | 1.5
Refrigerator | 1 | 26.6 cu ft | 2315 | 0.5
| 2 | 21.8 cu ft | 1300 | 0.5
| 3 | 17.9 cu ft | 770 | 0.5
Master Bath | 1 | Ascenti Gold Fixtures | 2160 | 2.5
| 2 | Moen Brass Collection | 1573 | 2.5
| 3 | Jacuzzi Whirlpool Spa | 1425 | 3
| 4 | Standard Chrome Fixtures | 992 | 2.5
Hall, Kitchen and Bath Tile | 1 | Level 3 | 1849 | 8
| 2 | Level 2 | 1381 | 5
| 3 | Level 1 | 913 | 3
Living/Bed-room Flooring | 1 | Hardwood Deluxe | 2001 | 10
| 2 | Premium Carpet | 1042 | 6
| 3 | Vinyl | 309 | 4
| 4 | Dirt floor | 0 | 0