## CB_DATA_ (hidden)
#NAME?

## Sheet2
Node | Description | Predecessor | Min | Mode | Max | Mean | StDev | Simulated Time | Start Time | End Time | Node | Time
A | Research User Requirements | NONE | 5 | 10 | 13 | 9 | 6 | 9 | 0 | 9 | A | 9
B | Prepare Project Requirement Document | A | 2 | 3 | 11 | 5 | 3 | 5 | 9 | 14 | B | 14
C | Prepare Technical Requirement Document | B | 2 | 9 | 14 | 8 | 5 | 8 | 14 | 22 | C | 22
D | Client Verification of TRD | C | 3 | 6 | 8 | 6 | 5 | 6 | 22 | 28 | D | 28
E | Development Phase | D | 1 | 4 | 5 | 3 | 1 | 3 | 28 | 31 | E | 31
F | Coding | E | 2 | 3 | 8 | 4 | 2 | 4 | 31 | 35 | F | 35
G | Unit Testing | F | 5 | 8 | 9 | 7 | 6 | 7 | 35 | 42 | G | 42
H | Quality Assurance Testing | G | 3 | 4 | 8 | 5 | 2 | 5 | 42 | 47 | H | 47
I | User Acceptance Test | H | 3 | 7 | 15 | 8 | 5 | 8 | 47 | 55 | I | 55
J | License Auditing | I | 1 | 9 | 15 | 8 | 4 | 8 | 55 | 63 | J | 63
K | Fix Glitches found in Verification | J, G1, G2 | 2 | 4 | 10 | 5 | 2 | 5 | 81 | 86 | K | 86
L | Plan for Release | K | 2 | 11 | 14 | 9 | 7 | 9 | 99 | 108 | L | 108
|  | Yes/No | Probability
| Is there a glitches? | 1 | 0%
| Description | Predecessor | Min | Mode | Max | Mean | StDev | Simulated Time | Start Time | End Time
G1 | Quality Assurance Testing | J | 3 | 4 | 8 | 5 | 2 | 9 | 81 | 90
G2 | Fix Gliches found in Verification | G1 | 2 | 4 | 10 | 5 | 2 | 9 | 90 | 99