## Gant
Colgate Palmolive: Gant
| Task | Subsidiary | Duration (days) | Predecessors | Resource | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185
1.1 | Finalize Development | Global | 10 |  | GIT | 5: 1.1
1.2 | Create Web Reports | Global | 5 | 1.1 | GIT | 13: 1.2
1.3 | Transport | Global | 1 | 1.2 | GIT | 17: 1.3
1.4 | Update documentation bundle | Global | 5 | 1.1 | GIT | 19: 1.4
1.5 | Create Training documentation | Global | 3 | 1.4 | GIT | 23: 1.5
2.1 | Subsidiary Questionnaire | Malaysia | 5 | 1.4 | SSO | 24: 2.1
2.2a | Identification of Resources | Malaysia | 1 | 1.4 | SSO | 27: 2.2a
2.2b | Identification of Resources | Malaysia | 1 | 1.4 | Business | 22: 2.2b
2.3 | Business Process Definition | Malaysia | 5 | 2.2 | Business | 25: 2.3
2.4a | Gap Analysis | Malaysia | 1 | 2.3 | GIT | 28: 2.4a
2.4b | Gap Analysis | Malaysia | 1 | 2.3 | SSO | 28: 2.4b
2.5a | Gap Recommendations | Malaysia | 1 | 2.4 | GIT | 29: 2.5a
2.5b | Gap Recommendations | Malaysia | 1 | 2.4 | SSO | 29: 2.5b
2.6a | Configuration of Data Warehouse | Malaysia | 3 | 2.5 | GIT | 31: 2.6a
2.6b | Configuration of Data Warehouse | Malaysia | 3 | 2.5 | SSO | 31: 2.6b
2.7 | Configuration of Transaction System | Malaysia | 5 | 2.5 | SSO | 35: 2.7
2.8 | Synchronize | Malaysia | 1 | 2.7 | GIT | 38: 2.8
2.9 | Unit Test | Malaysia | 3 | 2.8 | SSO | 40: 2.9
2.10a | Modify Configuration (1) | Malaysia | 1 | 2.9 | GIT | 42: 2.10a
2.10b | Modify Configuration (1) | Malaysia | 1 | 2.9 | SSO | 42: 2.10b
2.11 | Volume Test | Malaysia | 4 | 2.1 | SSO | 44: 2.11
2.12a | Modify Configuration (2) | Malaysia | 1 | 2.11 | GIT | 47: 2.12a
2.12b | Modify Configuration (2) | Malaysia | 1 | 2.11 | SSO | 47: 2.12b
2.13 | Data Validation | Malaysia | 15 | 2.12 | Business | 55: 2.13
2.14 | User Training | Malaysia | 5 | 2.13 | Business | 65: 2.14
2.15 | User Acceptance | Malaysia | 15 | 2.14 | SSO | 75: 2.15
2.16 | Go-Live | Malaysia | 1 | 2.15 | SSO | 83: 2.16
3.1 | Subsidiary Questionnaire | China | 5 | 1.4 | SSO | 50: 3.1
3.2a | Identification of Resources | China | 1 | 1.4 | SSO | 53: 3.2a
3.2b | Identification of Resources | China | 1 | 1.4 | Business | 22: 3.2b
3.3 | Business Process Definition | China | 5 | 3.2 | Business | 56: 3.3
3.4a | Gap Analysis | China | 1 | 3.3 | GIT | 59: 3.4a
3.4b | Gap Analysis | China | 1 | 3.3 | SSO | 59: 3.4b
3.5a | Gap Recommendations | China | 1 | 3.4 | GIT | 60: 3.5a
3.5b | Gap Recommendations | China | 1 | 3.4 | SSO | 60: 3.5b
3.6a | Configuration of Data Warehouse | China | 3 | 3.5 | GIT | 62: 3.6a
3.6b | Configuration of Data Warehouse | China | 3 | 3.5 | SSO | 62: 3.6b
3.7 | Configuration of Transaction System | China | 5 | 3.5 | SSO | 86: 3.7
3.8 | Synchronize | China | 1 | 3.7 | GIT | 89: 3.8
3.9 | Unit Test | China | 3 | 3.8 | SSO | 91: 3.9
3.10a | Modify Configuration (1) | China | 1 | 3.9 | GIT | 93: 3.10a
3.10b | Modify Configuration (1) | China | 1 | 3.9 | SSO | 93: 3.10b
3.11 | Volume Test | China | 4 | 3.1 | SSO | 95: 3.11
3.12a | Modify Configuration (2) | China | 1 | 3.11 | GIT | 98: 3.12a
3.12b | Modify Configuration (2) | China | 1 | 3.11 | SSO | 98: 3.12b
3.13 | Data Validation | China | 15 | 3.12 | Business | 106: 3.13
3.14 | User Training | China | 5 | 3.13 | Business | 116: 3.14
3.15 | User Acceptance | China | 15 | 3.14 | SSO | 126: 3.15
3.16 | Go-Live | China | 1 | 3.15 | SSO | 134: 3.16
4.1 | Subsidiary Questionnaire | Hong Kong | 5 | 1.4 | SSO | 101: 4.1
4.2a | Identification of Resources | Hong Kong | 1 | 1.4 | SSO | 104: 4.2a
4.2b | Identification of Resources | Hong Kong | 1 | 1.4 | Business | 22: 4.2b
4.3 | Business Process Definition | Hong Kong | 5 | 4.2 | Business | 107: 4.3
4.4a | Gap Analysis | Hong Kong | 1 | 4.3 | GIT | 110: 4.4a
4.4b | Gap Analysis | Hong Kong | 1 | 4.3 | SSO | 110: 4.4b
4.5a | Gap Recommendations | Hong Kong | 1 | 4.4 | GIT | 111: 4.5a
4.5b | Gap Recommendations | Hong Kong | 1 | 4.4 | SSO | 111: 4.5b
4.6a | Configuration of Data Warehouse | Hong Kong | 3 | 4.5 | GIT | 113: 4.6a
4.6b | Configuration of Data Warehouse | Hong Kong | 3 | 4.5 | SSO | 113: 4.6b
4.7 | Configuration of Transaction System | Hong Kong | 5 | 4.5 | SSO | 137: 4.7
4.8 | Synchronize | Hong Kong | 1 | 4.7 | GIT | 140: 4.8
4.9 | Unit Test | Hong Kong | 3 | 4.8 | SSO | 142: 4.9
4.10a | Modify Configuration (1) | Hong Kong | 1 | 4.9 | GIT | 144: 4.10a
4.10b | Modify Configuration (1) | Hong Kong | 1 | 4.9 | SSO | 144: 4.10b
4.11 | Volume Test | Hong Kong | 4 | 4.1 | SSO | 146: 4.11
4.12a | Modify Configuration (2) | Hong Kong | 1 | 4.11 | GIT | 149: 4.12a
4.12b | Modify Configuration (2) | Hong Kong | 1 | 4.11 | SSO | 149: 4.12b
4.13 | Data Validation | Hong Kong | 15 | 4.12 | Business | 157: 4.13
4.14 | User Training | Hong Kong | 5 | 4.13 | Business | 167: 3.14
4.15 | User Acceptance | Hong Kong | 15 | 4.14 | SSO | 177: 3.15
4.16 | Go-Live | Hong Kong | 1 | 4.15 | SSO | 185: 3.16

## Solver
Colgate Palmolive: Solver
[57 empty] | Total Days |  | 185
| Task | Subsidiary | Predecessors | Resource | 0 | 10 | 15 | 16 | 21 | 22 | 26 | 27 | 27 | 28 | 29 | 32 | 37 | 38 | 41 | 42 | 46 | 47 | 52 | 57 | 62 | 63 | 64 | 62 | 67 | 82 | 83 | 88 | 89 | 92 | 93 | 97 | 98 | 103 | 108 | 113 | 114 | 115 | 113 | 118 | 133 | 134 | 139 | 140 | 143 | 144 | 148 | 149 | 164 | 169 | 184 | 185 | Total |  | Duration
1.1 | Finalize Development | Global |  | GIT | -1 | 1 | [50 empty] | 10 | >= | 10
1.2 | Create Web Reports | Global | 1.1 | GIT |  | -1 | 1 | [49 empty] | 5 | >= | 5
1.3 | Transport | Global | 1.2 | GIT |  |  | -1 | 1 | [48 empty] | 1 | >= | 1
1.4 | Update documentation bundle | Global | 1.1 | GIT |  |  |  | -1 | 1 | [47 empty] | 5 | >= | 5
1.5 | Create Training documentation | Global | 1.4 | GIT |  |  |  |  | -1 | 0 | 0 | 0 | 1 | [43 empty] | 6 | >= | 3
2.1 | Subsidiary Questionnaire | Malaysia | 1.4 | SSO |  |  |  |  | -1 | 0 | 1 | [45 empty] | 5 | >= | 5
2.2a | Identification of Resources | Malaysia | 1.4 | SSO | [6 empty] | -1 | 1 | [44 empty] | 1 | >= | 1
2.2b | Identification of Resources | Malaysia | 1.4 | Business |  |  |  |  | -1 | 1 | [46 empty] | 1 | >= | 1
2.3 | Business Process Definition | Malaysia | 2.2 | Business | [5 empty] | -1 | 0 | 0 | 1 | [43 empty] | 5 | >= | 5
2.4a | Gap Analysis | Malaysia | 2.3 | GIT | [8 empty] | -1 | 1 | [42 empty] | 1 | >= | 1
2.4b | Gap Analysis | Malaysia | 2.3 | SSO | [8 empty] | -1 | 1 | [42 empty] | 1 | >= | 1
2.5a | Gap Recommendations | Malaysia | 2.4 | GIT | [9 empty] | -1 | 1 | [41 empty] | 1 | >= | 1
2.5b | Gap Recommendations | Malaysia | 2.4 | SSO | [9 empty] | -1 | 1 | [41 empty] | 1 | >= | 1
2.6a | Configuration of Data Warehouse | Malaysia | 2.5 | GIT | [10 empty] | -1 | 0 | 1 | [39 empty] | 8 | >= | 3
2.6b | Configuration of Data Warehouse | Malaysia | 2.5 | SSO | [10 empty] | -1 | 1 | [40 empty] | 3 | >= | 3
2.7 | Configuration of Transaction System | Malaysia | 2.5 | SSO | [11 empty] | -1 | 1 | [39 empty] | 5 | >= | 5
2.8 | Synchronize | Malaysia | 2.7 | GIT | [12 empty] | -1 | 1 | [38 empty] | 1 | >= | 1
2.9 | Unit Test | Malaysia | 2.8 | SSO | [13 empty] | -1 | 1 | [37 empty] | 3 | >= | 3
2.10a | Modify Configuration (1) | Malaysia | 2.9 | GIT | [14 empty] | -1 | 1 | [36 empty] | 1 | >= | 1
2.10b | Modify Configuration (1) | Malaysia | 2.9 | SSO | [14 empty] | -1 | 1 | [36 empty] | 1 | >= | 1
2.11 | Volume Test | Malaysia | 2.1 | SSO | [15 empty] | -1 | 1 | [35 empty] | 4 | >= | 4
2.12a | Modify Configuration (2) | Malaysia | 2.11 | GIT | [16 empty] | -1 | 1 | [34 empty] | 1 | >= | 1
2.12b | Modify Configuration (2) | Malaysia | 2.11 | SSO | [16 empty] | -1 | 1 | [34 empty] | 1 | >= | 1
2.13 | Data Validation | Malaysia | 2.12 | Business | [17 empty] | -1 | 0 | 0 | 0 | 0 | 0 | 1 | [28 empty] | 15 | >= | 15
2.14 | User Training | Malaysia | 2.13 | Business | [23 empty] | -1 | 1 | [27 empty] | 5 | >= | 5
2.15 | User Acceptance | Malaysia | 2.14 | SSO | [24 empty] | -1 | 1 | [26 empty] | 15 | >= | 15
2.16 | Go-Live | Malaysia | 2.15 | SSO | [25 empty] | -1 | 1 | [25 empty] | 1 | >= | 1
3.1 | Subsidiary Questionnaire | China | 1.4 | SSO | [17 empty] | -1 | 1 | [33 empty] | 5 | >= | 5
3.2a | Identification of Resources | China | 1.4 | SSO | [18 empty] | -1 | 1 | [32 empty] | 5 | >= | 1
3.2b | Identification of Resources | China | 1.4 | Business |  |  |  |  | -1 | 1 | [46 empty] | 1 | >= | 1
3.3 | Business Process Definition | China | 3.2 | Business | [19 empty] | -1 | 1 | [31 empty] | 5 | >= | 5
3.4a | Gap Analysis | China | 3.3 | GIT | [20 empty] | -1 | 1 | [30 empty] | 1 | >= | 1
3.4b | Gap Analysis | China | 3.3 | SSO | [20 empty] | -1 | 1 | [30 empty] | 1 | >= | 1
3.5a | Gap Recommendations | China | 3.4 | GIT | [21 empty] | -1 | 1 | [29 empty] | 1 | >= | 1
3.5b | Gap Recommendations | China | 3.4 | SSO | [21 empty] | -1 | 1 | [29 empty] | 1 | >= | 1
3.6a | Configuration of Data Warehouse | China | 3.5 | GIT | [22 empty] | -1 | 0 | 0 | 0 | 0 | 1 | [24 empty] | 24 | >= | 3
3.6b | Configuration of Data Warehouse | China | 3.5 | SSO | [22 empty] | -1 | 0 | 1 | [27 empty] | 3 | >= | 3
3.7 | Configuration of Transaction System | China | 3.5 | SSO | [26 empty] | -1 | 1 | [24 empty] | 5 | >= | 5
3.8 | Synchronize | China | 3.7 | GIT | [27 empty] | -1 | 1 | [23 empty] | 1 | >= | 1
3.9 | Unit Test | China | 3.8 | SSO | [28 empty] | -1 | 1 | [22 empty] | 3 | >= | 3
3.10a | Modify Configuration (1) | China | 3.9 | GIT | [29 empty] | -1 | 1 | [21 empty] | 1 | >= | 1
3.10b | Modify Configuration (1) | China | 3.9 | SSO | [29 empty] | -1 | 1 | [21 empty] | 1 | >= | 1
3.11 | Volume Test | China | 3.1 | SSO | [30 empty] | -1 | 1 | [20 empty] | 4 | >= | 4
3.12a | Modify Configuration (2) | China | 3.11 | GIT | [31 empty] | -1 | 1 | [19 empty] | 1 | >= | 1
3.12b | Modify Configuration (2) | China | 3.11 | SSO | [31 empty] | -1 | 1 | [19 empty] | 1 | >= | 1
3.13 | Data Validation | China | 3.12 | Business | [32 empty] | -1 | 0 | 0 | 0 | 0 | 0 | 1 | [13 empty] | 15 | >= | 15
3.14 | User Training | China | 3.13 | Business | [38 empty] | -1 | 1 | [12 empty] | 5 | >= | 5
3.15 | User Acceptance | China | 3.14 | SSO | [39 empty] | -1 | 1 | [11 empty] | 15 | >= | 15
3.16 | Go-Live | China | 3.15 | SSO | [40 empty] | -1 | 1 | [10 empty] | 1 | >= | 1
4.1 | Subsidiary Questionnaire | Hong Kong | 1.4 | SSO | [32 empty] | -1 | 1 | [18 empty] | 5 | >= | 5
4.2a | Identification of Resources | Hong Kong | 1.4 | SSO | [33 empty] | -1 | 1 | [17 empty] | 5 | >= | 1
4.2b | Identification of Resources | Hong Kong | 1.4 | Business |  |  |  |  | -1 | 1 | [46 empty] | 1 | >= | 1
4.3 | Business Process Definition | Hong Kong | 4.2 | Business | [34 empty] | -1 | 1 | [16 empty] | 5 | >= | 5
4.4a | Gap Analysis | Hong Kong | 4.3 | GIT | [35 empty] | -1 | 1 | [15 empty] | 1 | >= | 1
4.4b | Gap Analysis | Hong Kong | 4.3 | SSO | [35 empty] | -1 | 1 | [15 empty] | 1 | >= | 1
4.5a | Gap Recommendations | Hong Kong | 4.4 | GIT | [36 empty] | -1 | 1 | [14 empty] | 1 | >= | 1
4.5b | Gap Recommendations | Hong Kong | 4.4 | SSO | [36 empty] | -1 | 1 | [14 empty] | 1 | >= | 1
4.6a | Configuration of Data Warehouse | Hong Kong | 4.5 | GIT | [37 empty] | -1 | 0 | 0 | 0 | 0 | 1 | [9 empty] | 24 | >= | 3
4.6b | Configuration of Data Warehouse | Hong Kong | 4.5 | SSO | [37 empty] | -1 | 0 | 1 | [12 empty] | 3 | >= | 3
4.7 | Configuration of Transaction System | Hong Kong | 4.5 | SSO | [41 empty] | -1 | 1 | [9 empty] | 5 | >= | 5
4.8 | Synchronize | Hong Kong | 4.7 | GIT | [42 empty] | -1 | 1 | [8 empty] | 1 | >= | 1
4.9 | Unit Test | Hong Kong | 4.8 | SSO | [43 empty] | -1 | 1 | [7 empty] | 3 | >= | 3
4.10a | Modify Configuration (1) | Hong Kong | 4.9 | GIT | [44 empty] | -1 | 1 | [6 empty] | 1 | >= | 1
4.10b | Modify Configuration (1) | Hong Kong | 4.9 | SSO | [44 empty] | -1 | 1 | [6 empty] | 1 | >= | 1
4.11 | Volume Test | Hong Kong | 4.1 | SSO | [45 empty] | -1 | 1 | [5 empty] | 4 | >= | 4
4.12a | Modify Configuration (2) | Hong Kong | 4.11 | GIT | [46 empty] | -1 | 1 |  |  |  |  | 1 | >= | 1
4.12b | Modify Configuration (2) | Hong Kong | 4.11 | SSO | [46 empty] | -1 | 1 |  |  |  |  | 1 | >= | 1
4.13 | Data Validation | Hong Kong | 4.12 | Business | [47 empty] | -1 | 1 |  |  |  | 15 | >= | 15
4.14 | User Training | Hong Kong | 4.13 | Business | [48 empty] | -1 | 1 |  |  | 5 | >= | 5
4.15 | User Acceptance | Hong Kong | 4.14 | SSO | [49 empty] | -1 | 1 |  | 15 | >= | 15
4.16 | Go-Live | Hong Kong | 4.15 | SSO | [50 empty] | -1 | 1 | 1 | >= | 1

## Crashing
Colgate Palmolive: Cost Crashing | [57 empty] | Crashing Cost |  | 100000
[58 empty] | Max Complated Time |  | 148
| Task | Subsidiary | Predecessors | Resource | Duration | 0 | 10 | 15 | 16 | 21 | 22 | 24 | 25 | 27 | 28 | 29 | 31 | 34 | 35 | 37 | 38 | 40 | 41 | 44 | 46 | 51 | 55 | 59 | 56 | 61 | 69 | 70 | 73 | 74 | 76 | 77 | 79 | 80 | 83 | 87 | 92 | 93 | 98 | 95 | 100 | 108 | 109 | 112 | 113 | 115 | 116 | 118 | 119 | 134 | 139 | 147 | 148 | Total |  | Improved Duration | Resource | Basic Duration | Crash Time | Add'l FTE | Resource | Current FTE | Add'l FTE | Cost/FTE | Add'l Cost | FTE Days | Max Add'l FTE
1.1 | Finalize Development | Global |  | GIT | 10 | -1 | 1 | [50 empty] | 10 | >= | 10 | GIT | 10 | 0 | 0 | GIT | 1 | 0 | 100000 | 0 | 48 | 3
1.2 | Create Web Reports | Global | 1.1 | GIT | 5 |  | -1 | 1 | [49 empty] | 5 | >= | 5 | GIT | 5 | 0 | 0 | SSO | 1 | 1 | 100000 | 100000 | 123 | 3
1.3 | Transport | Global | 1.2 | GIT | 1 |  |  | -1 | 1 | [48 empty] | 1 | >= | 1 | GIT | 1 | 0 | 0 | RBU Malaysia | 0.5 | 0 | 100000 | 0 | 26 | 1
1.4 | Update documentation bundle | Global | 1.1 | GIT | 5 |  |  |  | -1 | 1 | [47 empty] | 5 | >= | 5 | GIT | 5 | 0 | 0 | RBU China | 0.5 | 0 | 100000 | 0 | 26 | 1
1.5 | Create Training documentation | Global | 1.4 | GIT | 3 |  |  |  |  | -1 | 0 | 0 | 0 | 1 | [43 empty] | 6 | >= | 3 | GIT | 3 | 0 | 0 | RBU Hong Kong | 0.5 | 0 | 100000 | 0 | 26 | 1
2.1 | Subsidiary Questionnaire | Malaysia | 1.4 | SSO | 5 |  |  |  |  | -1 | 0 | 1 | [45 empty] | 3 | >= | 2.5 | SSO | 5 | 2.5 | 1 |  |  |  |  | 100000
2.2a | Identification of Resources | Malaysia | 1.4 | SSO | 1 | [6 empty] | -1 | 1 | [44 empty] | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1 |  |  |  |  | <=
2.2b | Identification of Resources | Malaysia | 1.4 | Business | 1 |  |  |  |  | -1 | 1 | [46 empty] | 1 | >= | 1 | Business | 1 | 0 | 0 |  |  |  | Max Cost | 100000
2.3 | Business Process Definition | Malaysia | 2.2 | Business | 5 | [5 empty] | -1 | 0 | 0 | 1 | [43 empty] | 5 | >= | 5 | Business | 5 | 0 | 0
2.4a | Gap Analysis | Malaysia | 2.3 | GIT | 1 | [8 empty] | -1 | 1 | [42 empty] | 1 | >= | 1 | GIT | 1 | 0 | 0 |  | Add'l Cost | Project Duration
2.4b | Gap Analysis | Malaysia | 2.3 | SSO | 1 | [8 empty] | -1 | 1 | [42 empty] | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1 |  | 0 | 185
2.5a | Gap Recommendations | Malaysia | 2.4 | GIT | 1 | [9 empty] | -1 | 1 | [41 empty] | 1 | >= | 1 | GIT | 1 | 0 | 0 |  | 100000 | 148
2.5b | Gap Recommendations | Malaysia | 2.4 | SSO | 1 | [9 empty] | -1 | 1 | [41 empty] | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1 |  | 200000 | 132
2.6a | Configuration of Data Warehouse | Malaysia | 2.5 | GIT | 3 | [10 empty] | -1 | 0 | 1 | [39 empty] | 5 | >= | 3 | GIT | 3 | 0 | 0 |  | 300000 | Stopped
2.6b | Configuration of Data Warehouse | Malaysia | 2.5 | SSO | 3 | [10 empty] | -1 | 1 | [40 empty] | 2 | >= | 1.5 | SSO | 3 | 1.5 | 1 |  | 400000 | Stopped
2.7 | Configuration of Transaction System | Malaysia | 2.5 | SSO | 5 | [11 empty] | -1 | 1 | [39 empty] | 3 | >= | 2.5 | SSO | 5 | 2.5 | 1 |  | 500000 | Stopped
2.8 | Synchronize | Malaysia | 2.7 | GIT | 1 | [12 empty] | -1 | 1 | [38 empty] | 1 | >= | 1 | GIT | 1 | 0 | 0 |  | 600000 | Stopped
2.9 | Unit Test | Malaysia | 2.8 | SSO | 3 | [13 empty] | -1 | 1 | [37 empty] | 2 | >= | 1.5 | SSO | 3 | 1.5 | 1 |  | 700000 | Stopped
2.10a | Modify Configuration (1) | Malaysia | 2.9 | GIT | 1 | [14 empty] | -1 | 1 | [36 empty] | 1 | >= | 1 | GIT | 1 | 0 | 0 |  | 800000 | Stopped
2.10b | Modify Configuration (1) | Malaysia | 2.9 | SSO | 1 | [14 empty] | -1 | 1 | [36 empty] | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1 |  | 900000 | Stopped
2.11 | Volume Test | Malaysia | 2.1 | SSO | 4 | [15 empty] | -1 | 1 | [35 empty] | 2 | >= | 2 | SSO | 4 | 2 | 1
2.12a | Modify Configuration (2) | Malaysia | 2.11 | GIT | 1 | [16 empty] | -1 | 1 | [34 empty] | 1 | >= | 1 | GIT | 1 | 0 | 0
2.12b | Modify Configuration (2) | Malaysia | 2.11 | SSO | 1 | [16 empty] | -1 | 1 | [34 empty] | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1
2.13 | Data Validation | Malaysia | 2.12 | Business | 15 | [17 empty] | -1 | 0 | 0 | 0 | 0 | 0 | 1 | [28 empty] | 15 | >= | 15 | Business | 15 | 0 | 0
2.14 | User Training | Malaysia | 2.13 | Business | 5 | [23 empty] | -1 | 1 | [27 empty] | 5 | >= | 5 | Business | 5 | 0 | 0
2.15 | User Acceptance | Malaysia | 2.14 | SSO | 15 | [24 empty] | -1 | 1 | [26 empty] | 8 | >= | 7.5 | SSO | 15 | 7.5 | 1
2.16 | Go-Live | Malaysia | 2.15 | SSO | 1 | [25 empty] | -1 | 1 | [25 empty] | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1
3.1 | Subsidiary Questionnaire | China | 1.4 | SSO | 5 | [17 empty] | -1 | 1 | [33 empty] | 3 | >= | 2.5 | SSO | 5 | 2.5 | 1
3.2a | Identification of Resources | China | 1.4 | SSO | 1 | [18 empty] | -1 | 1 | [32 empty] | 2 | >= | 0.5 | SSO | 1 | 0.5 | 1
3.2b | Identification of Resources | China | 1.4 | Business | 1 |  |  |  |  | -1 | 1 | [46 empty] | 1 | >= | 1 | Business | 1 | 0 | 0
3.3 | Business Process Definition | China | 3.2 | Business | 5 | [19 empty] | -1 | 1 | [31 empty] | 5 | >= | 5 | Business | 5 | 0 | 0
3.4a | Gap Analysis | China | 3.3 | GIT | 1 | [20 empty] | -1 | 1 | [30 empty] | 4 | >= | 1 | GIT | 1 | 0 | 0
3.4b | Gap Analysis | China | 3.3 | SSO | 1 | [20 empty] | -1 | 1 | [30 empty] | 4 | >= | 0.5 | SSO | 1 | 0.5 | 1
3.5a | Gap Recommendations | China | 3.4 | GIT | 1 | [21 empty] | -1 | 1 | [29 empty] | 4 | >= | 1 | GIT | 1 | 0 | 0
3.5b | Gap Recommendations | China | 3.4 | SSO | 1 | [21 empty] | -1 | 1 | [29 empty] | 4 | >= | 0.5 | SSO | 1 | 0.5 | 1
3.6a | Configuration of Data Warehouse | China | 3.5 | GIT | 3 | [22 empty] | -1 | 0 | 0 | 0 | 0 | 1 | [24 empty] | 14 | >= | 3 | GIT | 3 | 0 | 0
3.6b | Configuration of Data Warehouse | China | 3.5 | SSO | 3 | [22 empty] | -1 | 0 | 1 | [27 empty] | 2 | >= | 1.5 | SSO | 3 | 1.5 | 1
3.7 | Configuration of Transaction System | China | 3.5 | SSO | 5 | [26 empty] | -1 | 1 | [24 empty] | 3 | >= | 2.5 | SSO | 5 | 2.5 | 1
3.8 | Synchronize | China | 3.7 | GIT | 1 | [27 empty] | -1 | 1 | [23 empty] | 1 | >= | 1 | GIT | 1 | 0 | 0
3.9 | Unit Test | China | 3.8 | SSO | 3 | [28 empty] | -1 | 1 | [22 empty] | 2 | >= | 1.5 | SSO | 3 | 1.5 | 1
3.10a | Modify Configuration (1) | China | 3.9 | GIT | 1 | [29 empty] | -1 | 1 | [21 empty] | 1 | >= | 1 | GIT | 1 | 0 | 0
3.10b | Modify Configuration (1) | China | 3.9 | SSO | 1 | [29 empty] | -1 | 1 | [21 empty] | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1
3.11 | Volume Test | China | 3.1 | SSO | 4 | [30 empty] | -1 | 1 | [20 empty] | 2 | >= | 2 | SSO | 4 | 2 | 1
3.12a | Modify Configuration (2) | China | 3.11 | GIT | 1 | [31 empty] | -1 | 1 | [19 empty] | 1 | >= | 1 | GIT | 1 | 0 | 0
3.12b | Modify Configuration (2) | China | 3.11 | SSO | 1 | [31 empty] | -1 | 1 | [19 empty] | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1
3.13 | Data Validation | China | 3.12 | Business | 15 | [32 empty] | -1 | 0 | 0 | 0 | 0 | 0 | 1 | [13 empty] | 15 | >= | 15 | Business | 15 | 0 | 0
3.14 | User Training | China | 3.13 | Business | 5 | [38 empty] | -1 | 1 | [12 empty] | 5 | >= | 5 | Business | 5 | 0 | 0
3.15 | User Acceptance | China | 3.14 | SSO | 15 | [39 empty] | -1 | 1 | [11 empty] | 8 | >= | 7.5 | SSO | 15 | 7.5 | 1
3.16 | Go-Live | China | 3.15 | SSO | 1 | [40 empty] | -1 | 1 | [10 empty] | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1
4.1 | Subsidiary Questionnaire | Hong Kong | 1.4 | SSO | 5 | [32 empty] | -1 | 1 | [18 empty] | 3 | >= | 2.5 | SSO | 5 | 2.5 | 1
4.2a | Identification of Resources | Hong Kong | 1.4 | SSO | 1 | [33 empty] | -1 | 1 | [17 empty] | 4 | >= | 0.5 | SSO | 1 | 0.5 | 1
4.2b | Identification of Resources | Hong Kong | 1.4 | Business | 1 |  |  |  |  | -1 | 1 | [46 empty] | 1 | >= | 1 | Business | 1 | 0 | 0
4.3 | Business Process Definition | Hong Kong | 4.2 | Business | 5 | [34 empty] | -1 | 1 | [16 empty] | 5 | >= | 5 | Business | 5 | 0 | 0
4.4a | Gap Analysis | Hong Kong | 4.3 | GIT | 1 | [35 empty] | -1 | 1 | [15 empty] | 1 | >= | 1 | GIT | 1 | 0 | 0
4.4b | Gap Analysis | Hong Kong | 4.3 | SSO | 1 | [35 empty] | -1 | 1 | [15 empty] | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1
4.5a | Gap Recommendations | Hong Kong | 4.4 | GIT | 1 | [36 empty] | -1 | 1 | [14 empty] | 5 | >= | 1 | GIT | 1 | 0 | 0
4.5b | Gap Recommendations | Hong Kong | 4.4 | SSO | 1 | [36 empty] | -1 | 1 | [14 empty] | 5 | >= | 0.5 | SSO | 1 | 0.5 | 1
4.6a | Configuration of Data Warehouse | Hong Kong | 4.5 | GIT | 3 | [37 empty] | -1 | 0 | 0 | 0 | 0 | 1 | [9 empty] | 14 | >= | 3 | GIT | 3 | 0 | 0
4.6b | Configuration of Data Warehouse | Hong Kong | 4.5 | SSO | 3 | [37 empty] | -1 | 0 | 1 | [12 empty] | 2 | >= | 1.5 | SSO | 3 | 1.5 | 1
4.7 | Configuration of Transaction System | Hong Kong | 4.5 | SSO | 5 | [41 empty] | -1 | 1 | [9 empty] | 3 | >= | 2.5 | SSO | 5 | 2.5 | 1
4.8 | Synchronize | Hong Kong | 4.7 | GIT | 1 | [42 empty] | -1 | 1 | [8 empty] | 1 | >= | 1 | GIT | 1 | 0 | 0
4.9 | Unit Test | Hong Kong | 4.8 | SSO | 3 | [43 empty] | -1 | 1 | [7 empty] | 2 | >= | 1.5 | SSO | 3 | 1.5 | 1
4.10a | Modify Configuration (1) | Hong Kong | 4.9 | GIT | 1 | [44 empty] | -1 | 1 | [6 empty] | 1 | >= | 1 | GIT | 1 | 0 | 0
4.10b | Modify Configuration (1) | Hong Kong | 4.9 | SSO | 1 | [44 empty] | -1 | 1 | [6 empty] | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1
4.11 | Volume Test | Hong Kong | 4.1 | SSO | 4 | [45 empty] | -1 | 1 | [5 empty] | 2 | >= | 2 | SSO | 4 | 2 | 1
4.12a | Modify Configuration (2) | Hong Kong | 4.11 | GIT | 1 | [46 empty] | -1 | 1 |  |  |  |  | 1 | >= | 1 | GIT | 1 | 0 | 0
4.12b | Modify Configuration (2) | Hong Kong | 4.11 | SSO | 1 | [46 empty] | -1 | 1 |  |  |  |  | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1
4.13 | Data Validation | Hong Kong | 4.12 | Business | 15 | [47 empty] | -1 | 1 |  |  |  | 15 | >= | 15 | Business | 15 | 0 | 0
4.14 | User Training | Hong Kong | 4.13 | Business | 5 | [48 empty] | -1 | 1 |  |  | 5 | >= | 5 | Business | 5 | 0 | 0
4.15 | User Acceptance | Hong Kong | 4.14 | SSO | 15 | [49 empty] | -1 | 1 |  | 8 | >= | 7.5 | SSO | 15 | 7.5 | 1
4.16 | Go-Live | Hong Kong | 4.15 | SSO | 1 | [50 empty] | -1 | 1 | 1 | >= | 0.5 | SSO | 1 | 0.5 | 1
Note on BG6: =(SUMPRODUCT(G6:BF6,$G$5:$BF$5))
Note on BI1: =BS11
Note on BI3: =BF5
Note on BI6: =BK6-BL6
Note on BL6: =BK6-(BK6/(1+BM6))
Note on BM12: =BQ7
Note on BP15: The input values are along the side, the output cell(s) are shown along the top
Note on BP16: Remember that the input cell is $BS$13
Note on BQ17: Solver found an integer solution within tolerance. All constraints are satisfied.
Note on BQ18: Solver found an integer solution within tolerance. All constraints are satisfied.
Note on BQ19: No solution after 3500 simulationns.
Note on BQ20: No solution after 3500 simulationns.
Note on BQ21: Solver stopped at user's request.
Note on BQ22: Solver stopped at user's request.
Note on BQ23: Solver stopped at user's request.
Note on BQ24: Solver stopped at user's request.
Note on BQ25: Solver stopped at user's request.
Note on BS6: =BQ6*BR6
Note on BS11: =SUM(BS6:BS10)
Note on BT7: =F11+F12+F16+F18+F20+F21+F23+F25+F26+F28+F31+F32+F33+F34+F38+F40+F42+F43+F45+F47+F48+F50+F53+F54+F55+F56+F60+F62+F64+F65+F67+F69+F70+F72+F75+F76