## Slide 1: Data Warehousing at Colgate Palmolive
Joshua Fluhr
David Foster
Manish Kumar
Victoria Lowther
Orly Shacham

## Slide 2: Global Technology at Colgate
Global information technology (GIT) department
Global IT solutions are used in Colgate subsidiaries around the world
Global model is rolled out to the regional subs
Notes: Colgate Palmolive uses a centralized Global Information Technology (GIT) department to create global IT solutions, subsequently used in Colgate subsidiaries around the world. After the global model is developed, a project is created and staffed in order to roll-out the global model to the regional subs.

## Slide 3: KPI Solution
KPI = key performance indicator
Tracks customer service
Creates consistency of KPI calculations across regions
Allows management to identify areas of needed improvement in the supply chain
Notes: Recently, Colgate developed a “key performance indicator” (KPI) solution to track customer service. This tool reports Colgate’s customer service by providing benchmarks such as the “% of orders shipped complete”, “% of orders on-time”, the “average customer order cycle time”, and many others. The goal of this tool is to create consistency of KPI calculations across regions, create transparency of data within and across regions, and create consolidation of reports. This in turn will allow management to identify areas of needed improvement in the supply chain throughout the Colgate world and implement the appropriate process change.

## Slide 4: The Challenge
Determine the most cost-effective way to install this KPI tool in all subsidiaries around the world
Notes: The challenge that Colgate IT now faces is to determine the most cost-effective way to install this KPI tool in all subsidiaries around the world. Although most regions use the same underlying transaction system, the way those systems are set-up and maintained differs from region to region. In addition, the customer order process can vary substantially between regions. So Colgate must take the time to review the business rules in each region and insure that there are no major gaps between the business assumptions used in the global model, and those used in the subsidiaries.

## Slide 5: Things to Consider
The countries can start the process in parallel
The same GIT (global information technology ) and SSO (shared service organizations) resources are utilized for all regions
Notes: Colgate IT is organized into one Global IT department (GIT) and several regional “shared service organizations” (SSO’s) The objective of the regional SSO is to provide local implementation support to Global initiatives and to provide full IT support to regional initiatives. Therefore, the roll-out of Customer Service KPI’s will require resources from GIT, the regional SSO, and the regional business users. Each SSO supports multiple countries in its region and is responsible for interfacing with the key business users and local IT staff at each location.
Colgate is trying to determine how long each region will take. The first region to be rolled out is Asia. The attached table shows a list of necessary tasks that must occur in order for each country to “go-live” with the Customer Service KPI tool.
There are some things to consider. First, the countries can start the process in parallel. So China and Malaysia can be rolling out the product simultaneously, for example. The same GIT and SSO resources are utilized for all regions. So there are constraints on their time. The total available resource from GIT is 1.0 full-time equivalents. The total available resource from the SSO is 1.0 full-time equivalents. The business resources for each subsidiary are independent of one another. The Malaysia business resource is not the same person as the China business resource, for example. Total business resources available are .5 full-time equivalents per country. For simplicity, we will assume that work begins in the second quarter of 2002. There are 5 working days in a week and no holidays. When will the roll-out of the 3 Asian countries be completed?

## Slide 6: First Approach - Excel

## Slide 7: Sample Data

## Slide 8: UGLY! – the Gant Chart . . .

## Slide 9: . . . & Solver!?

## Slide 10: . . . & more Solver!

## Slide 11: Solver Dialog Box

## Slide 12: Second Approach - Microsoft Project

## Slide 15: Cost Crashing

## Slide 16: Cost Crashing
Objective: to crash the project completion time per $100,000 additional cost

## Slide 17: Elementary Dear Watson
Improved Duration
= Basic Duration – Crash Time
Crash Time
= Basic Duration
– [Basic Duration/(1+Addl. FTE)]

## Slide 20: Solver Dialogue Box

## Slide 21: Solver Table Results

## Slide 22: Conclusion
With current assumptions, project ends in November
Project can be crashed back to August at a cost of $200,000
Project benefits are maximized when all subsidiaries are installed
These benefits are difficult to quantify

## Slide 23: Is It Worth It?
For just 3 subsidiaries, probably not
For 80 subsidiaries total, maybe