Managerial Problem

Colgate Palmolive uses a centralized Global Information Technology (GIT) department to create global IT solutions, subsequently used in Colgate subsidiaries around the world.  After the global model is developed, a project is created and staffed in order to rollout the global model to the regional subsidiaries.

Recently, Colgate developed a key performance indicator (KPI) solution to track customer service.  This tool reports Colgate’s customer service by providing benchmarks such as the percentage of orders shipped complete, percentage of orders on time, the average customer order cycle time, and many others.  The goal of this tool is to create consistency of KPI calculations across regions, create transparency of data within and across regions, and create consolidation of reports.  This in turn will allow management to identify areas of needed improvement in the supply chain throughout the Colgate world and implement the appropriate process change.

The challenge that Colgate IT now faces is to determine the most cost-effective way to install this KPI tool in all subsidiaries around the world.  Although most regions use the same underlying transaction system, the way those systems are set-up and maintained differs from region to region.  In addition, the customer order process can vary substantially between regions.  So Colgate must take the time to review the business rules in each region and insure that there are no major gaps between the business assumptions used in the global model, and those used in the subsidiaries.

Colgate IT is organized into one Global IT department (GIT) and several regional shared service organizations (SSO’s).  The objective of the regional SSO is to provide local implementation support to Global initiatives and to provide full IT support to regional initiatives.  Therefore, the rollout of Customer Service KPI’s will require resources from GIT, the regional SSO, and the regional business users.  Each SSO supports multiple countries in its region and is responsible for interfacing with the key business users and local IT staff at each location.

Colgate is trying to determine how long each region will take.  The first region to be rolled out is Asia.  There are some things to consider.  First, the countries can start the process in parallel.  So China and Malaysia can be rolling out the product simultaneously, for example.  The same GIT and SSO resources are utilized for all regions.  So there are constraints on their time.  The total available resource from GIT is 1.0 full-time equivalent.  The total available resource from the SSO is 1.0 full-time equivalent.  The business resources for each subsidiary are independent of one another.  The Malaysia business resource is not the same person as the China business resource, for example.  Total business resources available are .5 full-time equivalents per country.

## Alternatives

In order to determine the most cost effective way to install the KPI tools in all subsidiaries around the world we took two approaches.  We both developed both a gant chart and solver table in Excel and developed a chart and schedule in Microsoft project based on the following assumptions:

- The project starts in the second quarter of 2002

- There are 5 working days in a week and no holidays

- Each step must come after its predecessor

- A resource cannot be simultaneously working on two tasks at the same time (There is only one GIT and one SSO resources, although there is one local resource per country).

Although we got the same time forecast in both Excel and Project, it was significantly easier in Project.  However, we were able to come up with cost crashing figures in Excel and MS Project did not give us the ability to see the cost implications of adding additional resources.  In Excel we found that given the above assumptions, the rollout of KPI in Asia will be completed in November using either the Excel or Microsoft Project model.  The project could be completed by August if Colgate Palmolive is willing to spend an additional $200,000.

## Conclusion

The benefits of the implementing KPIs in subsidiaries is maximized when the rollout is complete, but the benefits are hard to quantify and it may not be worth it for just 3 subsidiaries.  However, the picture changes when you are looking at 80 subsidiaries.  If there are resource constraints on other projects that are more easily quantified, and resources can be pulled from this project once it completes, that might be a reason for cost crashing.