Decision Models

Professor Juran

Component based system migration

Presentation

Business Problem

Insurance companies were among the first to adopt computer technology.  The majority of these companies have monolithic systems.  These systems are designed to address one or more business processes (e.g. Claims handling) and include all necessary functions.  Companies have many (often hundreds) of these systems. Function or business rules are hereby repeated many times which makes the extension and maintenance of these system very costly and lengthy. Companies are looking to replace the older systems with new ones to achieve competitive advantages, reduce costs etc.

Figure 1: Insurance Systems and their dependencies

Figure 1 shows a typical systems portfolio and their dependencies.

Component based development

In recent years companies have adopted the idea of component based development. A component does not implement an entire business process, but only certain related functions.  A Party component e.g. could include all the necessary functions to administrate persons and organizations and the roles they play for the company (e.g. Policy Holder, Insured etc.) Each function is only implemented once.  If a component needs to use that function it access the component that implements it, rather than replicating it.

Figure 2: Component Hierarchy

Figure 2 shows a typical set of reusable components.

No single component covers an entire business process. Therefore multiple components are needed to cover the functions of a single system. Since components and systems have dependencies, determining the sequence in which to replace which system with which component can be tricky. Not all systems can be replaced at once, so system interfaces might be required to integrate new components with old systems.

Step 1- Parameters setup

Table 1 sets up (1) components’ hierarchy, and (2) time to build each component. Table 2 sets up (3) costs of interfaces between new components and old systems and (4) cost of delays per unit of time if the deadline for delivering new systems is passed. Example:

Claim

Communication

Agreement

Party

Physical Object

Common

Dependent of

Communication system

Health Policy system

New components

Systems

|  |  | Table 1 - New components dependencies |  |  |  |  |  | Table 2 - Cost of interfacing new components with old systems |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| New components |  | Communic. | Party | Common | Claim | Agreement | Object | Life Policy Admin | Health Policy Admin | Claim | Life Policy Admin 2 | Customer information |
| Communic. | Dep.on | 0 | 1 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 100 |
| Party | Dep.on | 0 | 0 | 1 | 0 | 0 | 0 | 200 | 150 | 150 | 0 | 100 |
| Common |  | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 150 | 170 | 220 | 100 |
| Claim | Dep.on | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 170 | 220 | 0 |
| Agreement | Dep.on | 0 | 1 | 0 | 0 | 0 | 1 | 200 | 150 | 210 | 220 | 0 |
| Object | Dep.on | 0 | 0 | 1 | 0 | 0 | 0 | 200 | 150 | 0 | 220 | 100 |
| Time to build |  | 10 | 11 | 5 | 19 | 18 | 9 |  |  |  |  |  |
| Deadline |  |  |  |  |  |  |  | 100 | 100 | 100 | 100 | 100 |
| Cost of delays per time unit |  |  |  |  |  |  |  | 10 | 20 | 5 | 10 | 18 |

Step 2- Components and Systems sequencing

Step 2.1- Basically, the solver generates a set of 6 consecutive integers from #1 to #6 (decision variables in blue cells) and “randomly” attributed to each component (in the rest of this document, Ci# and Sj# will design the sequence order of component i and system j, respectively). The pink cell checks for the uniqueness of the 6 numbers and must be 0 (checked by a solver constraint)

Step 2.2- This sequence is checked to be compliant with component hierarchy. For instance, if Party component is dependent upon Common component, Party can be implemented before Common.

These conditions are individually checked for each possible couple of component in Table 3: if C1 depends on C2 (from table 1) then C1# must be greater or equal to C2#. Solver constraints are defined so that all these conditions must be checked for each sequence generated.

Step 2.3- Once a sequence of component has been checked, table 4 deducts the sequencing of new systems based on the following rules:

A system can migrate to a “new system”, only once all its new components have been implemented. Thus, the implementation of a new system relies upon the availability of the last new component involved in this system. In the meantime, an old system must be specifically interfaced with any new components it would rely upon. In table 3 the appropriate Ci# is attributed for each component involved in a specific system Sj, and Sj# = MAX(Ci#) (green cells).

|  |  | Table 3 - New components sequencing |  |  |  |  |  | Table 4 - New systems sequencing |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Communic. | Party | Common | Claim | Agreement | Object | Life Policy Admin | Health Policy Admin | Claim | Life Policy Admin 2 | Customer information |
| Sequencing | 0 | 4 | 3 | 1 | 6 | 5 | 2 | 5 | 5 | 6 | 6 | 4 |
| Communic. | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 |
| Party | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 3 |
| Common | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 |
| Claim | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 6 | 6 | 0 |
| Agreement | 5 | 0 | 2 | 0 | 0 | 0 | 3 | 5 | 5 | 5 | 5 | 0 |
| Object | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 2 |

Step 3- Costs

Step 3.1- Table 5 determines the scheduling of deliveries for the different components, and thus for the new systems.

Table is ordered by ascending component sequencing number (=VLOOKUP() instructions). The development of The scheduling of components’ deliveries is thus incremented by individual times to build new components as define in table 1. As seen previously, a system delivery is equal to the delivery date of its last new component.

For each system, the delay is compared to the deadline as define in table 2, and the cost of delays is incremented accordingly (green cells-table 5)

Step 3.2- Table 6 determines the cost of interfacing new components with old systems. A cost of interface is incurred if a new component is available before the whole system. A system’s last component is by definition available at the same time as the new system, thus no extra cost is incurred. If Sj depends on Ci and if Ci is lower than Sj then cost of interface should be incremented (green cells-table 6)

For instance, Life Policy Admin (#5) is implemented as soon as Agreement component is available (#5). Thus, there is no cost for interfacing Agreement, but there is a cost (200) for interfacing the first four new components Common, Object, Party and Communication with the old Life Policy Admin system.

Costs of delays and costs of interfaces are tallied (red cell) and must be minimized by the solver.

|  |  | Table 5 - Cost of delays |  |  |  |  |  | Table 6 - Cost of interfaces |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sequence of components implementation |  | Scheduling of deliveries | Life Policy Admin | Health Policy Admin | Claim | Life Policy Admin 2 | Customer information | Life Policy Admin | Health Policy Admin | Claim | Life Policy Admin 2 | Customer information |
| Common | 1 | 5 | 5 | 0 | 0 | 0 | 5 | 200 | 150 | 170 | 220 | 0 |
| Object | 2 | 14 | 14 | 14 | 14 | 0 | 14 | 200 | 150 | 0 | 220 | 0 |
| Party | 3 | 25 | 25 | 25 | 25 | 25 | 25 | 200 | 150 | 150 | 0 | 0 |
| Communic. | 4 | 35 | 0 | 0 | 35 | 35 | 0 | 200 | 0 | 0 | 0 | 0 |
| Agreement | 5 | 53 | 53 | 53 | 53 | 53 | 0 | 0 | 0 | 210 | 220 | 0 |
| Claim | 6 | 72 | 72 | 72 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 |
| Total costs |  | 2440 | 0 | 0 | 0 | 0 | 0 | 800 | 450 | 530 | 660 | 0 |

Step 4- Setup of the Standard Evolutionary Solver

Solution

The solution displayed in the following graphs

Exhibit A- Full model

|  |  | Table 1 - New components dependencies |  |  |  |  |  | Table 2 - Cost of interfacing new components with old systems |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| New components |  | Communic. | Party | Common | Claim | Agreement | Object | Life Policy Admin | Health Policy Admin | Claim | Life Policy Admin 2 | Customer information |
| Communic. | Dep.on | 0 | 1 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 100 |
| Party | Dep.on | 0 | 0 | 1 | 0 | 0 | 0 | 200 | 150 | 150 | 0 | 100 |
| Common |  | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 150 | 170 | 220 | 100 |
| Claim | Dep.on | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 170 | 220 | 0 |
| Agreement | Dep.on | 0 | 1 | 0 | 0 | 0 | 1 | 200 | 150 | 210 | 220 | 0 |
| Object | Dep.on | 0 | 0 | 1 | 0 | 0 | 0 | 200 | 150 | 0 | 220 | 100 |
| Time to build |  | 10 | 11 | 5 | 19 | 18 | 9 |  |  |  |  |  |
| Deadline |  |  |  |  |  |  |  | 100 | 100 | 100 | 100 | 100 |
| Cost of delays per time unit |  |  |  |  |  |  |  | 10 | 20 | 5 | 10 | 18 |
|  |  | Table 3 - New components sequencing |  |  |  |  |  | Table 4 - New systems sequencing |  |  |  |  |
|  |  | Communic. | Party | Common | Claim | Agreement | Object | Life Policy Admin | Health Policy Admin | Claim | Life Policy Admin 2 | Customer information |
| Sequencing | 0 | 4 | 3 | 1 | 6 | 5 | 2 | 5 | 5 | 6 | 6 | 4 |
| Communic. | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 |
| Party | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 3 |
| Common | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 |
| Claim | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 6 | 6 | 0 |
| Agreement | 5 | 0 | 2 | 0 | 0 | 0 | 3 | 5 | 5 | 5 | 5 | 0 |
| Object | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 2 |
|  |  | Table 5 - Cost of delays |  |  |  |  |  | Table 6 - Cost of interfaces |  |  |  |  |
| Sequence of components implementation |  | Scheduling of deliveries | Life Policy Admin | Health Policy Admin | Claim | Life Policy Admin 2 | Customer information | Life Policy Admin | Health Policy Admin | Claim | Life Policy Admin 2 | Customer information |
| Common | 1 | 5 | 5 | 0 | 0 | 0 | 5 | 200 | 150 | 170 | 220 | 0 |
| Object | 2 | 14 | 14 | 14 | 14 | 0 | 14 | 200 | 150 | 0 | 220 | 0 |
| Party | 3 | 25 | 25 | 25 | 25 | 25 | 25 | 200 | 150 | 150 | 0 | 0 |
| Communic. | 4 | 35 | 0 | 0 | 35 | 35 | 0 | 200 | 0 | 0 | 0 | 0 |
| Agreement | 5 | 53 | 53 | 53 | 53 | 53 | 0 | 0 | 0 | 210 | 220 | 0 |
| Claim | 6 | 72 | 72 | 72 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 |
| Total costs |  | 2440 | 0 | 0 | 0 | 0 | 0 | 800 | 450 | 530 | 660 | 0 |